## Project Charter
Project Charter
Define scope, objectives, and secure formal approval before delivery begins
📌 PROJECT INFORMATION
Project Name | CRM Platform Migration | 💡 Short, descriptive name used across all docs
Project ID | PRJ-2024-007 | 💡 From your PMO registry
Project Manager | Sarah Chen
Sponsor | Rachel Torres, CEO | 💡 Executive with budget authority
Start Date | 2024-01-08
Target End Date | 2024-06-30
Budget | $450,000 | 💡 Internal costs + vendors + contingency
💼 BUSINESS CASE
Problem Statement | Current CRM is end-of-life, causing data silos across Sales, Support, and Marketing — 40% manual reconciliation work weekly.
Proposed Solution | Migrate to modern cloud CRM (Salesforce) with automated workflows, unified customer data model, and direct ERP integration.
Expected Benefits | 30% reduction in admin overhead; single source of truth; improved pipeline reporting for exec team.
ROI Estimate | 18-month payback. Estimated $200K annual savings from process automation and headcount redeployment. | 💡 Include assumptions
🎯 OBJECTIVES (SMART)
Objective 1 | Migrate all customer data (180K records) with zero data loss, validated by automated reconciliation report
Objective 2 | Achieve 90% user adoption within 60 days of go-live, measured by weekly login data
Objective 3 | Reduce manual data entry tasks by 50% by end of Q3 2024
Objective 4 | Deliver ERP + marketing integrations by go-live with no critical defects
📐 SCOPE
In Scope | Data migration (all active records); user training (100 users); integrations: ERP, email; custom reporting (5 dashboards)
Out of Scope | Marketing automation rebuild; mobile app; historical data >5 years; partner portal | 💡 Document explicitly to prevent scope creep
👥 KEY STAKEHOLDERS
Sponsor | Rachel Torres — Final approval, budget authority, escalation owner
Product Owner | Tom Nguyen — Requirements sign-off, UAT approval, change control
Technical Lead | David Kim — Architecture decisions, integration design, build quality
Change Manager | Maria Lopez — Training plan, communications, adoption measurement
🏁 KEY MILESTONES
Requirements Complete | 2024-02-15
Architecture Approved | 2024-03-01
Development Complete | 2024-05-01
UAT Complete | 2024-05-31
Training Complete | 2024-06-15
Go-Live | 2024-06-30
📎 ASSUMPTIONS & CONSTRAINTS
Assumption 1 | Client IT team provides dedicated resource for integration support throughout
Assumption 2 | Legacy CRM data exportable in CSV format without specialist tooling
Constraint 1 | Must comply with GDPR data residency — no data leaves EU region
Constraint 2 | Go-live cannot occur during Q4 commercial freeze (Oct 1 – Nov 30)
⚠️ TOP RISKS AT INITIATION
Risk 1 | Data quality issues in legacy system extend migration timeline — MEDIUM prob, HIGH impact
Risk 2 | User resistance to new system threatens adoption targets — MEDIUM prob, MEDIUM impact
Risk 3 | ERP integration complexity requires additional budget — LOW prob, HIGH impact
✅ APPROVAL & SIGN-OFF
Sponsor Signature |  | 💡 By signing, sponsor authorises project funding
Date Approved
PM Signature
Date