## 90_Projects (hidden)
ProjectID | PortfolioID | ProjectName | Sponsor | PM | Department | StrategicObjective | Stage | RAG | HealthScore | StartDate | BaselineFinish | ForecastFinish | Budget | Actual | Committed | PercentComplete | Priority | EscalationFlag | StatusFreshnessDays
PRJ-001 | Transformation | ERP Stabilization | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 86 | 2026-01-05 | 2026-04-05 | 2026-04-03 | 180 | 112 | 22 | 0.18 | High | Yes | 1
PRJ-002 | Customer Experience | Client Portal Redesign | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 85 | 2026-01-11 | 2026-04-15 | 2026-04-14 | 198 | 129 | 28 | 0.25 | Medium | No | 2
PRJ-003 | Operations Excellence | Finance Automation | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 84 | 2026-01-17 | 2026-04-25 | 2026-04-25 | 216 | 147 | 35 | 0.32 | Medium | No | 3
PRJ-004 | Data & Analytics | Data Warehouse Refresh | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-01-23 | 2026-05-05 | 2026-05-06 | 234 | 166 | 42 | 0.39 | High | No | 4
PRJ-005 | Regulatory Change | Compliance Uplift | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-01-29 | 2026-05-15 | 2026-05-17 | 252 | 186 | 30 | 0.46 | Low | No | 5
PRJ-006 | Product Delivery | Contact Center Optimization | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 47 | 2026-02-04 | 2026-05-25 | 2026-05-28 | 270 | 208 | 38 | 0.53 | High | Yes | 6
PRJ-007 | Transformation | ServiceNow Rollout | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 80 | 2026-02-10 | 2026-06-04 | 2026-06-08 | 288 | 230 | 46 | 0.6 | High | No | 7
PRJ-008 | Customer Experience | Sales Forecast Model | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 79 | 2026-02-16 | 2026-06-14 | 2026-06-19 | 306 | 190 | 55 | 0.67 | Medium | No | 8
PRJ-009 | Operations Excellence | Procurement Controls | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 86 | 2026-02-22 | 2026-06-24 | 2026-06-30 | 324 | 211 | 39 | 0.74 | Medium | No | 1
PRJ-010 | Data & Analytics | HR Self-Service | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-02-28 | 2026-07-04 | 2026-07-11 | 342 | 233 | 48 | 0.81 | High | No | 2
PRJ-011 | Regulatory Change | Mobile App Release | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-03-06 | 2026-06-04 | 2026-07-22 | 360 | 256 | 58 | 0.18 | Low | No | 3
PRJ-012 | Product Delivery | Cloud Cost Optimization | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 45 | 2026-03-12 | 2026-06-14 | 2026-08-02 | 378 | 280 | 68 | 0.25 | High | Yes | 4
PRJ-013 | Transformation | Portfolio Intake Revamp | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 82 | 2026-03-18 | 2026-06-24 | 2026-06-14 | 396 | 305 | 48 | 0.32 | High | No | 5
PRJ-014 | Customer Experience | Steering Committee Pack | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 81 | 2026-03-24 | 2026-07-04 | 2026-06-25 | 414 | 331 | 58 | 0.39 | Medium | No | 6
PRJ-015 | Operations Excellence | Security Hardening | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 80 | 2026-03-30 | 2026-07-14 | 2026-07-06 | 432 | 268 | 69 | 0.46 | Medium | No | 7
PRJ-016 | Data & Analytics | CRM Data Quality | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-04-05 | 2026-07-24 | 2026-07-17 | 450 | 293 | 81 | 0.53 | High | No | 8
PRJ-017 | Regulatory Change | Resource Planning Model | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-04-11 | 2026-08-03 | 2026-07-28 | 468 | 318 | 56 | 0.6 | Low | No | 1
PRJ-018 | Product Delivery | Customer Onboarding | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 47 | 2026-04-17 | 2026-08-13 | 2026-08-08 | 486 | 345 | 68 | 0.67 | High | Yes | 2
PRJ-019 | Transformation | Billing Reconciliation | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 84 | 2026-04-23 | 2026-08-23 | 2026-08-19 | 504 | 373 | 81 | 0.74 | High | No | 3
PRJ-020 | Customer Experience | Vendor Integration | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 83 | 2026-04-29 | 2026-09-02 | 2026-08-30 | 522 | 402 | 94 | 0.81 | Medium | No | 4
PRJ-021 | Operations Excellence | Product Discovery | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 82 | 2026-05-05 | 2026-08-03 | 2026-09-10 | 540 | 432 | 65 | 0.18 | Medium | No | 5
PRJ-022 | Data & Analytics | Analytics Governance | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-05-11 | 2026-08-13 | 2026-09-21 | 558 | 346 | 78 | 0.25 | High | No | 6
PRJ-023 | Regulatory Change | Retention Campaign | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-05-17 | 2026-08-23 | 2026-10-02 | 576 | 374 | 92 | 0.32 | Low | Yes | 7
PRJ-024 | Product Delivery | Operational Dashboard | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 45 | 2026-05-23 | 2026-09-02 | 2026-10-13 | 594 | 404 | 107 | 0.39 | High | Yes | 8
PRJ-025 | Transformation | Policy Refresh | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 86 | 2026-05-29 | 2026-09-12 | 2026-08-25 | 612 | 435 | 73 | 0.46 | High | No | 1
PRJ-026 | Customer Experience | API Gateway | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 85 | 2026-06-04 | 2026-09-22 | 2026-09-05 | 630 | 466 | 88 | 0.53 | Medium | No | 2
PRJ-027 | Operations Excellence | Knowledge Base | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 84 | 2026-06-10 | 2026-10-02 | 2026-09-16 | 648 | 499 | 104 | 0.6 | Medium | No | 3
PRJ-028 | Data & Analytics | Workflow Simplification | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-06-16 | 2026-10-12 | 2026-09-27 | 666 | 533 | 120 | 0.67 | High | No | 4
PRJ-029 | Regulatory Change | Audit Readiness | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-06-22 | 2026-10-22 | 2026-10-08 | 684 | 424 | 82 | 0.74 | Low | No | 5
PRJ-030 | Product Delivery | Release Train | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 47 | 2026-06-28 | 2026-11-01 | 2026-10-19 | 702 | 456 | 98 | 0.81 | High | Yes | 6
PRJ-031 | Transformation | Benefits Tracking | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 80 | 2026-07-04 | 2026-10-02 | 2026-10-30 | 720 | 490 | 115 | 0.18 | High | No | 7
PRJ-032 | Customer Experience | PMO Operating Model | C. Bennett | S. Hall | Finance | Revenue Growth | Planning | Green | 79 | 2026-07-10 | 2026-10-12 | 2026-11-10 | 738 | 524 | 133 | 0.25 | Medium | No | 8
PRJ-033 | Operations Excellence | Capacity Planning | D. Kim | A. Khan | Marketing | Customer Experience | Delivery | Green | 86 | 2026-07-16 | 2026-10-22 | 2026-11-21 | 756 | 559 | 91 | 0.32 | Medium | No | 1
PRJ-034 | Data & Analytics | Change Request Hub | S. Chen | M. Singh | Operations | Risk Reduction | Delivery | Amber | 68 | 2026-07-22 | 2026-11-01 | 2026-12-02 | 774 | 596 | 108 | 0.39 | High | Yes | 2
PRJ-035 | Regulatory Change | Milestone Tracker | M. Lopez | J. Patel | Legal | Digital Enablement | Closing | Amber | 67 | 2026-07-28 | 2026-11-11 | 2026-12-13 | 792 | 634 | 127 | 0.46 | Low | No | 3
PRJ-036 | Product Delivery | Decision Log | R. Torres | L. Wong | HR | Data Modernization | Delivery | Red | 45 | 2026-08-03 | 2026-11-21 | 2026-12-24 | 810 | 502 | 146 | 0.53 | High | Yes | 4
PRJ-037 | Transformation | Executive Reporting | A. Rahman | N. Ibrahim | IT | Operational Efficiency | Initiation | Green | 82 | 2026-08-09 | 2026-12-01 | 2026-11-05 | 828 | 538 | 99 | 0.6 | High | No | 5

## 90_Milestones (hidden)
MilestoneID | ProjectID | MilestoneName | PlannedDate | ForecastDate | ActualDate | Status | CriticalFlag | Owner
MS-001-1 | PRJ-001 | Kickoff | 2026-01-19 | 2026-01-21 | 2026-01-18 | Complete | No | N. Ibrahim
MS-001-2 | PRJ-001 | Build | 2026-02-06 | 2026-02-12 | 2026-02-05 | On track | No | N. Ibrahim
MS-001-3 | PRJ-001 | UAT | 2026-02-24 | 2026-02-26 |  | At risk | Yes | N. Ibrahim
MS-001-4 | PRJ-001 | Go-live | 2026-03-14 | 2026-03-20 |  | Pending | Yes | N. Ibrahim
MS-002-1 | PRJ-002 | Kickoff | 2026-01-25 | 2026-01-27 | 2026-01-24 | Complete | No | S. Hall
MS-002-2 | PRJ-002 | Build | 2026-02-12 | 2026-02-18 | 2026-02-11 | On track | No | S. Hall
MS-002-3 | PRJ-002 | UAT | 2026-03-02 | 2026-03-04 |  | At risk | Yes | S. Hall
MS-002-4 | PRJ-002 | Go-live | 2026-03-20 | 2026-03-26 |  | Pending | Yes | S. Hall
MS-003-1 | PRJ-003 | Kickoff | 2026-01-31 | 2026-02-02 | 2026-01-30 | Complete | No | A. Khan
MS-003-2 | PRJ-003 | Build | 2026-02-18 | 2026-02-24 | 2026-02-17 | On track | No | A. Khan
MS-003-3 | PRJ-003 | UAT | 2026-03-08 | 2026-03-10 |  | At risk | Yes | A. Khan
MS-003-4 | PRJ-003 | Go-live | 2026-03-26 | 2026-04-01 |  | Pending | Yes | A. Khan
MS-004-1 | PRJ-004 | Kickoff | 2026-02-06 | 2026-02-08 | 2026-02-05 | Complete | No | M. Singh
MS-004-2 | PRJ-004 | Build | 2026-02-24 | 2026-03-02 | 2026-02-23 | On track | No | M. Singh
MS-004-3 | PRJ-004 | UAT | 2026-03-14 | 2026-03-16 |  | At risk | Yes | M. Singh
MS-004-4 | PRJ-004 | Go-live | 2026-04-01 | 2026-04-07 |  | Pending | Yes | M. Singh
MS-005-1 | PRJ-005 | Kickoff | 2026-02-12 | 2026-02-14 | 2026-02-11 | Complete | No | J. Patel
MS-005-2 | PRJ-005 | Build | 2026-03-02 | 2026-03-08 | 2026-03-01 | On track | No | J. Patel
MS-005-3 | PRJ-005 | UAT | 2026-03-20 | 2026-03-22 |  | At risk | Yes | J. Patel
MS-005-4 | PRJ-005 | Go-live | 2026-04-07 | 2026-04-13 |  | Pending | Yes | J. Patel
MS-006-1 | PRJ-006 | Kickoff | 2026-02-18 | 2026-02-20 | 2026-02-17 | Complete | No | L. Wong
MS-006-2 | PRJ-006 | Build | 2026-03-08 | 2026-03-14 | 2026-03-07 | On track | No | L. Wong
MS-006-3 | PRJ-006 | UAT | 2026-03-26 | 2026-03-28 |  | At risk | Yes | L. Wong
MS-006-4 | PRJ-006 | Go-live | 2026-04-13 | 2026-04-19 |  | Pending | Yes | L. Wong
MS-007-1 | PRJ-007 | Kickoff | 2026-02-24 | 2026-02-26 | 2026-02-23 | Complete | No | N. Ibrahim
MS-007-2 | PRJ-007 | Build | 2026-03-14 | 2026-03-20 | 2026-03-13 | On track | No | N. Ibrahim
MS-007-3 | PRJ-007 | UAT | 2026-04-01 | 2026-04-03 |  | At risk | Yes | N. Ibrahim
MS-007-4 | PRJ-007 | Go-live | 2026-04-19 | 2026-04-25 |  | Pending | Yes | N. Ibrahim
MS-008-1 | PRJ-008 | Kickoff | 2026-03-02 | 2026-03-04 | 2026-03-01 | Complete | No | S. Hall
MS-008-2 | PRJ-008 | Build | 2026-03-20 | 2026-03-26 | 2026-03-19 | On track | No | S. Hall
MS-008-3 | PRJ-008 | UAT | 2026-04-07 | 2026-04-09 |  | At risk | Yes | S. Hall
MS-008-4 | PRJ-008 | Go-live | 2026-04-25 | 2026-05-01 |  | Pending | Yes | S. Hall
MS-009-1 | PRJ-009 | Kickoff | 2026-03-08 | 2026-03-10 | 2026-03-07 | Complete | No | A. Khan
MS-009-2 | PRJ-009 | Build | 2026-03-26 | 2026-04-01 | 2026-03-25 | On track | No | A. Khan
MS-009-3 | PRJ-009 | UAT | 2026-04-13 | 2026-04-15 |  | At risk | Yes | A. Khan
MS-009-4 | PRJ-009 | Go-live | 2026-05-01 | 2026-05-07 |  | Pending | Yes | A. Khan
MS-010-1 | PRJ-010 | Kickoff | 2026-03-14 | 2026-03-16 | 2026-03-13 | Complete | No | M. Singh
MS-010-2 | PRJ-010 | Build | 2026-04-01 | 2026-04-07 | 2026-03-31 | On track | No | M. Singh
MS-010-3 | PRJ-010 | UAT | 2026-04-19 | 2026-04-21 |  | At risk | Yes | M. Singh
MS-010-4 | PRJ-010 | Go-live | 2026-05-07 | 2026-05-13 |  | Pending | Yes | M. Singh
MS-011-1 | PRJ-011 | Kickoff | 2026-03-20 | 2026-03-22 | 2026-03-19 | Complete | No | J. Patel
MS-011-2 | PRJ-011 | Build | 2026-04-07 | 2026-04-13 | 2026-04-06 | On track | No | J. Patel
MS-011-3 | PRJ-011 | UAT | 2026-04-25 | 2026-04-27 |  | At risk | Yes | J. Patel
MS-011-4 | PRJ-011 | Go-live | 2026-05-13 | 2026-05-19 |  | Pending | Yes | J. Patel
MS-012-1 | PRJ-012 | Kickoff | 2026-03-26 | 2026-03-28 | 2026-03-25 | Complete | No | L. Wong
MS-012-2 | PRJ-012 | Build | 2026-04-13 | 2026-04-19 | 2026-04-12 | On track | No | L. Wong
MS-012-3 | PRJ-012 | UAT | 2026-05-01 | 2026-05-03 |  | At risk | Yes | L. Wong
MS-012-4 | PRJ-012 | Go-live | 2026-05-19 | 2026-05-25 |  | Pending | Yes | L. Wong
MS-013-1 | PRJ-013 | Kickoff | 2026-04-01 | 2026-04-03 | 2026-03-31 | Complete | No | N. Ibrahim
MS-013-2 | PRJ-013 | Build | 2026-04-19 | 2026-04-25 | 2026-04-18 | On track | No | N. Ibrahim
MS-013-3 | PRJ-013 | UAT | 2026-05-07 | 2026-05-09 |  | At risk | Yes | N. Ibrahim
MS-013-4 | PRJ-013 | Go-live | 2026-05-25 | 2026-05-31 |  | Pending | Yes | N. Ibrahim
MS-014-1 | PRJ-014 | Kickoff | 2026-04-07 | 2026-04-09 | 2026-04-06 | Complete | No | S. Hall
MS-014-2 | PRJ-014 | Build | 2026-04-25 | 2026-05-01 | 2026-04-24 | On track | No | S. Hall
MS-014-3 | PRJ-014 | UAT | 2026-05-13 | 2026-05-15 |  | At risk | Yes | S. Hall
MS-014-4 | PRJ-014 | Go-live | 2026-05-31 | 2026-06-06 |  | Pending | Yes | S. Hall
MS-015-1 | PRJ-015 | Kickoff | 2026-04-13 | 2026-04-15 | 2026-04-12 | Complete | No | A. Khan
MS-015-2 | PRJ-015 | Build | 2026-05-01 | 2026-05-07 | 2026-04-30 | On track | No | A. Khan
MS-015-3 | PRJ-015 | UAT | 2026-05-19 | 2026-05-21 |  | At risk | Yes | A. Khan
MS-015-4 | PRJ-015 | Go-live | 2026-06-06 | 2026-06-12 |  | Pending | Yes | A. Khan
MS-016-1 | PRJ-016 | Kickoff | 2026-04-19 | 2026-04-21 | 2026-04-18 | Complete | No | M. Singh
MS-016-2 | PRJ-016 | Build | 2026-05-07 | 2026-05-13 | 2026-05-06 | On track | No | M. Singh
MS-016-3 | PRJ-016 | UAT | 2026-05-25 | 2026-05-27 |  | At risk | Yes | M. Singh
MS-016-4 | PRJ-016 | Go-live | 2026-06-12 | 2026-06-18 |  | Pending | Yes | M. Singh
MS-017-1 | PRJ-017 | Kickoff | 2026-04-25 | 2026-04-27 | 2026-04-24 | Complete | No | J. Patel
MS-017-2 | PRJ-017 | Build | 2026-05-13 | 2026-05-19 | 2026-05-12 | On track | No | J. Patel
MS-017-3 | PRJ-017 | UAT | 2026-05-31 | 2026-06-02 |  | At risk | Yes | J. Patel
MS-017-4 | PRJ-017 | Go-live | 2026-06-18 | 2026-06-24 |  | Pending | Yes | J. Patel
MS-018-1 | PRJ-018 | Kickoff | 2026-05-01 | 2026-05-03 | 2026-04-30 | Complete | No | L. Wong
MS-018-2 | PRJ-018 | Build | 2026-05-19 | 2026-05-25 | 2026-05-18 | On track | No | L. Wong
MS-018-3 | PRJ-018 | UAT | 2026-06-06 | 2026-06-08 |  | At risk | Yes | L. Wong
MS-018-4 | PRJ-018 | Go-live | 2026-06-24 | 2026-06-30 |  | Pending | Yes | L. Wong
MS-019-1 | PRJ-019 | Kickoff | 2026-05-07 | 2026-05-09 | 2026-05-06 | Complete | No | N. Ibrahim
MS-019-2 | PRJ-019 | Build | 2026-05-25 | 2026-05-31 | 2026-05-24 | On track | No | N. Ibrahim
MS-019-3 | PRJ-019 | UAT | 2026-06-12 | 2026-06-14 |  | At risk | Yes | N. Ibrahim
MS-019-4 | PRJ-019 | Go-live | 2026-06-30 | 2026-07-06 |  | Pending | Yes | N. Ibrahim
MS-020-1 | PRJ-020 | Kickoff | 2026-05-13 | 2026-05-15 | 2026-05-12 | Complete | No | S. Hall
MS-020-2 | PRJ-020 | Build | 2026-05-31 | 2026-06-06 | 2026-05-30 | On track | No | S. Hall
MS-020-3 | PRJ-020 | UAT | 2026-06-18 | 2026-06-20 |  | At risk | Yes | S. Hall
MS-020-4 | PRJ-020 | Go-live | 2026-07-06 | 2026-07-12 |  | Pending | Yes | S. Hall
MS-021-1 | PRJ-021 | Kickoff | 2026-05-19 | 2026-05-21 | 2026-05-18 | Complete | No | A. Khan
MS-021-2 | PRJ-021 | Build | 2026-06-06 | 2026-06-12 | 2026-06-05 | On track | No | A. Khan
MS-021-3 | PRJ-021 | UAT | 2026-06-24 | 2026-06-26 |  | At risk | Yes | A. Khan
MS-021-4 | PRJ-021 | Go-live | 2026-07-12 | 2026-07-18 |  | Pending | Yes | A. Khan
MS-022-1 | PRJ-022 | Kickoff | 2026-05-25 | 2026-05-27 | 2026-05-24 | Complete | No | M. Singh
MS-022-2 | PRJ-022 | Build | 2026-06-12 | 2026-06-18 | 2026-06-11 | On track | No | M. Singh
MS-022-3 | PRJ-022 | UAT | 2026-06-30 | 2026-07-02 |  | At risk | Yes | M. Singh
MS-022-4 | PRJ-022 | Go-live | 2026-07-18 | 2026-07-24 |  | Pending | Yes | M. Singh
MS-023-1 | PRJ-023 | Kickoff | 2026-05-31 | 2026-06-02 | 2026-05-30 | Complete | No | J. Patel
MS-023-2 | PRJ-023 | Build | 2026-06-18 | 2026-06-24 | 2026-06-17 | On track | No | J. Patel
MS-023-3 | PRJ-023 | UAT | 2026-07-06 | 2026-07-08 |  | At risk | Yes | J. Patel
MS-023-4 | PRJ-023 | Go-live | 2026-07-24 | 2026-07-30 |  | Pending | Yes | J. Patel
MS-024-1 | PRJ-024 | Kickoff | 2026-06-06 | 2026-06-08 | 2026-06-05 | Complete | No | L. Wong
MS-024-2 | PRJ-024 | Build | 2026-06-24 | 2026-06-30 | 2026-06-23 | On track | No | L. Wong
MS-024-3 | PRJ-024 | UAT | 2026-07-12 | 2026-07-14 |  | At risk | Yes | L. Wong
MS-024-4 | PRJ-024 | Go-live | 2026-07-30 | 2026-08-05 |  | Pending | Yes | L. Wong
MS-025-1 | PRJ-025 | Kickoff | 2026-06-12 | 2026-06-14 | 2026-06-11 | Complete | No | N. Ibrahim
MS-025-2 | PRJ-025 | Build | 2026-06-30 | 2026-07-06 | 2026-06-29 | On track | No | N. Ibrahim
MS-025-3 | PRJ-025 | UAT | 2026-07-18 | 2026-07-20 |  | At risk | Yes | N. Ibrahim
MS-025-4 | PRJ-025 | Go-live | 2026-08-05 | 2026-08-11 |  | Pending | Yes | N. Ibrahim
MS-026-1 | PRJ-026 | Kickoff | 2026-06-18 | 2026-06-20 | 2026-06-17 | Complete | No | S. Hall
MS-026-2 | PRJ-026 | Build | 2026-07-06 | 2026-07-12 | 2026-07-05 | On track | No | S. Hall
MS-026-3 | PRJ-026 | UAT | 2026-07-24 | 2026-07-26 |  | At risk | Yes | S. Hall
MS-026-4 | PRJ-026 | Go-live | 2026-08-11 | 2026-08-17 |  | Pending | Yes | S. Hall
MS-027-1 | PRJ-027 | Kickoff | 2026-06-24 | 2026-06-26 | 2026-06-23 | Complete | No | A. Khan
MS-027-2 | PRJ-027 | Build | 2026-07-12 | 2026-07-18 | 2026-07-11 | On track | No | A. Khan
MS-027-3 | PRJ-027 | UAT | 2026-07-30 | 2026-08-01 |  | At risk | Yes | A. Khan
MS-027-4 | PRJ-027 | Go-live | 2026-08-17 | 2026-08-23 |  | Pending | Yes | A. Khan
MS-028-1 | PRJ-028 | Kickoff | 2026-06-30 | 2026-07-02 | 2026-06-29 | Complete | No | M. Singh
MS-028-2 | PRJ-028 | Build | 2026-07-18 | 2026-07-24 | 2026-07-17 | On track | No | M. Singh
MS-028-3 | PRJ-028 | UAT | 2026-08-05 | 2026-08-07 |  | At risk | Yes | M. Singh
MS-028-4 | PRJ-028 | Go-live | 2026-08-23 | 2026-08-29 |  | Pending | Yes | M. Singh
MS-029-1 | PRJ-029 | Kickoff | 2026-07-06 | 2026-07-08 | 2026-07-05 | Complete | No | J. Patel
MS-029-2 | PRJ-029 | Build | 2026-07-24 | 2026-07-30 | 2026-07-23 | On track | No | J. Patel
MS-029-3 | PRJ-029 | UAT | 2026-08-11 | 2026-08-13 |  | At risk | Yes | J. Patel
MS-029-4 | PRJ-029 | Go-live | 2026-08-29 | 2026-09-04 |  | Pending | Yes | J. Patel
MS-030-1 | PRJ-030 | Kickoff | 2026-07-12 | 2026-07-14 | 2026-07-11 | Complete | No | L. Wong
MS-030-2 | PRJ-030 | Build | 2026-07-30 | 2026-08-05 | 2026-07-29 | On track | No | L. Wong
MS-030-3 | PRJ-030 | UAT | 2026-08-17 | 2026-08-19 |  | At risk | Yes | L. Wong
MS-030-4 | PRJ-030 | Go-live | 2026-09-04 | 2026-09-10 |  | Pending | Yes | L. Wong
MS-031-1 | PRJ-031 | Kickoff | 2026-07-18 | 2026-07-20 | 2026-07-17 | Complete | No | N. Ibrahim
MS-031-2 | PRJ-031 | Build | 2026-08-05 | 2026-08-11 | 2026-08-04 | On track | No | N. Ibrahim
MS-031-3 | PRJ-031 | UAT | 2026-08-23 | 2026-08-25 |  | At risk | Yes | N. Ibrahim
MS-031-4 | PRJ-031 | Go-live | 2026-09-10 | 2026-09-16 |  | Pending | Yes | N. Ibrahim
MS-032-1 | PRJ-032 | Kickoff | 2026-07-24 | 2026-07-26 | 2026-07-23 | Complete | No | S. Hall
MS-032-2 | PRJ-032 | Build | 2026-08-11 | 2026-08-17 | 2026-08-10 | On track | No | S. Hall
MS-032-3 | PRJ-032 | UAT | 2026-08-29 | 2026-08-31 |  | At risk | Yes | S. Hall
MS-032-4 | PRJ-032 | Go-live | 2026-09-16 | 2026-09-22 |  | Pending | Yes | S. Hall
MS-033-1 | PRJ-033 | Kickoff | 2026-07-30 | 2026-08-01 | 2026-07-29 | Complete | No | A. Khan
MS-033-2 | PRJ-033 | Build | 2026-08-17 | 2026-08-23 | 2026-08-16 | On track | No | A. Khan
MS-033-3 | PRJ-033 | UAT | 2026-09-04 | 2026-09-06 |  | At risk | Yes | A. Khan
MS-033-4 | PRJ-033 | Go-live | 2026-09-22 | 2026-09-28 |  | Pending | Yes | A. Khan
MS-034-1 | PRJ-034 | Kickoff | 2026-08-05 | 2026-08-07 | 2026-08-04 | Complete | No | M. Singh
MS-034-2 | PRJ-034 | Build | 2026-08-23 | 2026-08-29 | 2026-08-22 | On track | No | M. Singh
MS-034-3 | PRJ-034 | UAT | 2026-09-10 | 2026-09-12 |  | At risk | Yes | M. Singh
MS-034-4 | PRJ-034 | Go-live | 2026-09-28 | 2026-10-04 |  | Pending | Yes | M. Singh
MS-035-1 | PRJ-035 | Kickoff | 2026-08-11 | 2026-08-13 | 2026-08-10 | Complete | No | J. Patel
MS-035-2 | PRJ-035 | Build | 2026-08-29 | 2026-09-04 | 2026-08-28 | On track | No | J. Patel
MS-035-3 | PRJ-035 | UAT | 2026-09-16 | 2026-09-18 |  | At risk | Yes | J. Patel
MS-035-4 | PRJ-035 | Go-live | 2026-10-04 | 2026-10-10 |  | Pending | Yes | J. Patel
MS-036-1 | PRJ-036 | Kickoff | 2026-08-17 | 2026-08-19 | 2026-08-16 | Complete | No | L. Wong
MS-036-2 | PRJ-036 | Build | 2026-09-04 | 2026-09-10 | 2026-09-03 | On track | No | L. Wong
MS-036-3 | PRJ-036 | UAT | 2026-09-22 | 2026-09-24 |  | At risk | Yes | L. Wong
MS-036-4 | PRJ-036 | Go-live | 2026-10-10 | 2026-10-16 |  | Pending | Yes | L. Wong
MS-037-1 | PRJ-037 | Kickoff | 2026-08-23 | 2026-08-25 | 2026-08-22 | Complete | No | N. Ibrahim
MS-037-2 | PRJ-037 | Build | 2026-09-10 | 2026-09-16 | 2026-09-09 | On track | No | N. Ibrahim
MS-037-3 | PRJ-037 | UAT | 2026-09-28 | 2026-09-30 |  | At risk | Yes | N. Ibrahim
MS-037-4 | PRJ-037 | Go-live | 2026-10-16 | 2026-10-22 |  | Pending | Yes | N. Ibrahim

## 90_Risks (hidden)
RiskID | ProjectID | Category | Likelihood | Impact | Score | Owner | Mitigation | DueDate | Status | AgingDays | EscalatedFlag
RK-001-1 | PRJ-001 | Delivery | 2 | 3 | 6 | A. Rahman | Mitigate erp stabilization risk 1 | 2026-02-04 | Closed | 5 | No
RK-001-2 | PRJ-001 | Commercial | 3 | 4 | 12 | A. Rahman | Mitigate erp stabilization risk 2 | 2026-02-11 | Monitoring | 6 | No
RK-002-1 | PRJ-002 | Commercial | 3 | 4 | 12 | C. Bennett | Mitigate client portal redesign risk 1 | 2026-02-09 | Monitoring | 6 | No
RK-003-1 | PRJ-003 | Technical | 4 | 5 | 20 | D. Kim | Mitigate finance automation risk 1 | 2026-02-14 | Open | 7 | Yes
RK-004-1 | PRJ-004 | Resource | 5 | 2 | 10 | S. Chen | Mitigate data warehouse refresh risk 1 | 2026-02-19 | Monitoring | 8 | No
RK-004-2 | PRJ-004 | Change | 2 | 3 | 6 | S. Chen | Mitigate data warehouse refresh risk 2 | 2026-02-26 | Closed | 9 | No
RK-005-1 | PRJ-005 | Change | 2 | 3 | 6 | M. Lopez | Mitigate compliance uplift risk 1 | 2026-02-24 | Closed | 9 | No
RK-006-1 | PRJ-006 | Delivery | 3 | 4 | 12 | R. Torres | Mitigate contact center optimization risk 1 | 2026-03-01 | Monitoring | 10 | No
RK-007-1 | PRJ-007 | Commercial | 4 | 5 | 20 | A. Rahman | Mitigate servicenow rollout risk 1 | 2026-03-06 | Open | 11 | Yes
RK-007-2 | PRJ-007 | Technical | 5 | 2 | 10 | A. Rahman | Mitigate servicenow rollout risk 2 | 2026-03-13 | Monitoring | 12 | No
RK-008-1 | PRJ-008 | Technical | 5 | 2 | 10 | C. Bennett | Mitigate sales forecast model risk 1 | 2026-03-11 | Monitoring | 12 | No
RK-009-1 | PRJ-009 | Resource | 2 | 3 | 6 | D. Kim | Mitigate procurement controls risk 1 | 2026-03-16 | Closed | 13 | No
RK-010-1 | PRJ-010 | Change | 3 | 4 | 12 | S. Chen | Mitigate hr self-service risk 1 | 2026-03-21 | Monitoring | 14 | No
RK-010-2 | PRJ-010 | Delivery | 4 | 5 | 20 | S. Chen | Mitigate hr self-service risk 2 | 2026-03-28 | Open | 15 | Yes
RK-011-1 | PRJ-011 | Delivery | 4 | 5 | 20 | M. Lopez | Mitigate mobile app release risk 1 | 2026-03-26 | Open | 15 | Yes
RK-012-1 | PRJ-012 | Commercial | 5 | 2 | 10 | R. Torres | Mitigate cloud cost optimization risk 1 | 2026-03-31 | Monitoring | 16 | No
RK-013-1 | PRJ-013 | Technical | 2 | 3 | 6 | A. Rahman | Mitigate portfolio intake revamp risk 1 | 2026-04-05 | Closed | 17 | No
RK-013-2 | PRJ-013 | Resource | 3 | 4 | 12 | A. Rahman | Mitigate portfolio intake revamp risk 2 | 2026-04-12 | Monitoring | 18 | No
RK-014-1 | PRJ-014 | Resource | 3 | 4 | 12 | C. Bennett | Mitigate steering committee pack risk 1 | 2026-04-10 | Monitoring | 18 | No
RK-015-1 | PRJ-015 | Change | 4 | 5 | 20 | D. Kim | Mitigate security hardening risk 1 | 2026-04-15 | Open | 19 | Yes
RK-016-1 | PRJ-016 | Delivery | 5 | 2 | 10 | S. Chen | Mitigate crm data quality risk 1 | 2026-04-20 | Monitoring | 20 | No
RK-016-2 | PRJ-016 | Commercial | 2 | 3 | 6 | S. Chen | Mitigate crm data quality risk 2 | 2026-04-27 | Closed | 21 | No
RK-017-1 | PRJ-017 | Commercial | 2 | 3 | 6 | M. Lopez | Mitigate resource planning model risk 1 | 2026-04-25 | Closed | 21 | No
RK-018-1 | PRJ-018 | Technical | 3 | 4 | 12 | R. Torres | Mitigate customer onboarding risk 1 | 2026-04-30 | Monitoring | 22 | No
RK-019-1 | PRJ-019 | Resource | 4 | 5 | 20 | A. Rahman | Mitigate billing reconciliation risk 1 | 2026-05-05 | Open | 23 | Yes
RK-019-2 | PRJ-019 | Change | 5 | 2 | 10 | A. Rahman | Mitigate billing reconciliation risk 2 | 2026-05-12 | Monitoring | 24 | No
RK-020-1 | PRJ-020 | Change | 5 | 2 | 10 | C. Bennett | Mitigate vendor integration risk 1 | 2026-05-10 | Monitoring | 24 | No
RK-021-1 | PRJ-021 | Delivery | 2 | 3 | 6 | D. Kim | Mitigate product discovery risk 1 | 2026-05-15 | Closed | 25 | No
RK-022-1 | PRJ-022 | Commercial | 3 | 4 | 12 | S. Chen | Mitigate analytics governance risk 1 | 2026-05-20 | Monitoring | 26 | No
RK-022-2 | PRJ-022 | Technical | 4 | 5 | 20 | S. Chen | Mitigate analytics governance risk 2 | 2026-05-27 | Open | 5 | Yes
RK-023-1 | PRJ-023 | Technical | 4 | 5 | 20 | M. Lopez | Mitigate retention campaign risk 1 | 2026-05-25 | Open | 5 | Yes
RK-024-1 | PRJ-024 | Resource | 5 | 2 | 10 | R. Torres | Mitigate operational dashboard risk 1 | 2026-05-30 | Monitoring | 6 | No
RK-025-1 | PRJ-025 | Change | 2 | 3 | 6 | A. Rahman | Mitigate policy refresh risk 1 | 2026-06-04 | Closed | 7 | No
RK-025-2 | PRJ-025 | Delivery | 3 | 4 | 12 | A. Rahman | Mitigate policy refresh risk 2 | 2026-06-11 | Monitoring | 8 | No
RK-026-1 | PRJ-026 | Delivery | 3 | 4 | 12 | C. Bennett | Mitigate api gateway risk 1 | 2026-06-09 | Monitoring | 8 | No
RK-027-1 | PRJ-027 | Commercial | 4 | 5 | 20 | D. Kim | Mitigate knowledge base risk 1 | 2026-06-14 | Open | 9 | Yes
RK-028-1 | PRJ-028 | Technical | 5 | 2 | 10 | S. Chen | Mitigate workflow simplification risk 1 | 2026-06-19 | Monitoring | 10 | No
RK-028-2 | PRJ-028 | Resource | 2 | 3 | 6 | S. Chen | Mitigate workflow simplification risk 2 | 2026-06-26 | Closed | 11 | No
RK-029-1 | PRJ-029 | Resource | 2 | 3 | 6 | M. Lopez | Mitigate audit readiness risk 1 | 2026-06-24 | Closed | 11 | No
RK-030-1 | PRJ-030 | Change | 3 | 4 | 12 | R. Torres | Mitigate release train risk 1 | 2026-06-29 | Monitoring | 12 | No
RK-031-1 | PRJ-031 | Delivery | 4 | 5 | 20 | A. Rahman | Mitigate benefits tracking risk 1 | 2026-07-04 | Open | 13 | Yes
RK-031-2 | PRJ-031 | Commercial | 5 | 2 | 10 | A. Rahman | Mitigate benefits tracking risk 2 | 2026-07-11 | Monitoring | 14 | No
RK-032-1 | PRJ-032 | Commercial | 5 | 2 | 10 | C. Bennett | Mitigate pmo operating model risk 1 | 2026-07-09 | Monitoring | 14 | No
RK-033-1 | PRJ-033 | Technical | 2 | 3 | 6 | D. Kim | Mitigate capacity planning risk 1 | 2026-07-14 | Closed | 15 | No
RK-034-1 | PRJ-034 | Resource | 3 | 4 | 12 | S. Chen | Mitigate change request hub risk 1 | 2026-07-19 | Monitoring | 16 | No
RK-034-2 | PRJ-034 | Change | 4 | 5 | 20 | S. Chen | Mitigate change request hub risk 2 | 2026-07-26 | Open | 17 | Yes
RK-035-1 | PRJ-035 | Change | 4 | 5 | 20 | M. Lopez | Mitigate milestone tracker risk 1 | 2026-07-24 | Open | 17 | Yes
RK-036-1 | PRJ-036 | Delivery | 5 | 2 | 10 | R. Torres | Mitigate decision log risk 1 | 2026-07-29 | Monitoring | 18 | No
RK-037-1 | PRJ-037 | Commercial | 2 | 3 | 6 | A. Rahman | Mitigate executive reporting risk 1 | 2026-08-03 | Closed | 19 | No
RK-037-2 | PRJ-037 | Technical | 3 | 4 | 12 | A. Rahman | Mitigate executive reporting risk 2 | 2026-08-10 | Monitoring | 20 | No

## 90_Issues (hidden)
IssueID | ProjectID | Severity | Priority | OpenDate | DueDate | Owner | ResolutionPlan | Status | AgingDays | DecisionRequired
IS-001 | PRJ-001 | Major | High | 2026-01-17 | 2026-01-29 | N. Ibrahim | Resolve erp stabilization blockers through PMO escalation | In progress | 4 | Yes
IS-003 | PRJ-003 | Major | Medium | 2026-01-25 | 2026-02-06 | A. Khan | Resolve finance automation blockers through PMO escalation | In progress | 10 | No
IS-005 | PRJ-005 | Major | Low | 2026-02-02 | 2026-02-14 | J. Patel | Resolve compliance uplift blockers through PMO escalation | In progress | 16 | Yes
IS-007 | PRJ-007 | Major | High | 2026-02-10 | 2026-02-22 | N. Ibrahim | Resolve servicenow rollout blockers through PMO escalation | In progress | 22 | No
IS-009 | PRJ-009 | Major | Medium | 2026-02-18 | 2026-03-02 | A. Khan | Resolve procurement controls blockers through PMO escalation | In progress | 8 | Yes
IS-011 | PRJ-011 | Major | Low | 2026-02-26 | 2026-03-10 | J. Patel | Resolve mobile app release blockers through PMO escalation | In progress | 14 | No
IS-013 | PRJ-013 | Major | High | 2026-03-06 | 2026-03-18 | N. Ibrahim | Resolve portfolio intake revamp blockers through PMO escalation | In progress | 20 | Yes
IS-015 | PRJ-015 | Major | Medium | 2026-03-14 | 2026-03-26 | A. Khan | Resolve security hardening blockers through PMO escalation | In progress | 6 | No
IS-017 | PRJ-017 | Major | Low | 2026-03-22 | 2026-04-03 | J. Patel | Resolve resource planning model blockers through PMO escalation | In progress | 12 | Yes
IS-019 | PRJ-019 | Major | High | 2026-03-30 | 2026-04-11 | N. Ibrahim | Resolve billing reconciliation blockers through PMO escalation | In progress | 18 | No
IS-021 | PRJ-021 | Major | Medium | 2026-04-07 | 2026-04-19 | A. Khan | Resolve product discovery blockers through PMO escalation | In progress | 4 | Yes
IS-023 | PRJ-023 | Major | Low | 2026-04-15 | 2026-04-27 | J. Patel | Resolve retention campaign blockers through PMO escalation | In progress | 10 | No
IS-025 | PRJ-025 | Major | High | 2026-04-23 | 2026-05-05 | N. Ibrahim | Resolve policy refresh blockers through PMO escalation | In progress | 16 | Yes
IS-027 | PRJ-027 | Major | Medium | 2026-05-01 | 2026-05-13 | A. Khan | Resolve knowledge base blockers through PMO escalation | In progress | 22 | No
IS-029 | PRJ-029 | Major | Low | 2026-05-09 | 2026-05-21 | J. Patel | Resolve audit readiness blockers through PMO escalation | In progress | 8 | Yes
IS-031 | PRJ-031 | Major | High | 2026-05-17 | 2026-05-29 | N. Ibrahim | Resolve benefits tracking blockers through PMO escalation | In progress | 14 | No
IS-033 | PRJ-033 | Major | Medium | 2026-05-25 | 2026-06-06 | A. Khan | Resolve capacity planning blockers through PMO escalation | In progress | 20 | Yes
IS-035 | PRJ-035 | Major | Low | 2026-06-02 | 2026-06-14 | J. Patel | Resolve milestone tracker blockers through PMO escalation | In progress | 6 | No
IS-037 | PRJ-037 | Major | High | 2026-06-10 | 2026-06-22 | N. Ibrahim | Resolve executive reporting blockers through PMO escalation | In progress | 12 | Yes

## 90_BusinessCases (hidden)
BusinessCaseID | ProjectID | CaseStatus | ExpectedBenefit | NPV | IRR | PaybackMonths | ApprovalStage | BenefitOwner | AssumptionConfidence | ApprovalDate
BC-001 | PRJ-001 | Approved | 120 | 80 | 0.16 | 9 | SteerCo | A. Rahman | High | 2026-01-15
BC-002 | PRJ-002 | Pending | 134 | 90 | 0.17 | 10 | Finance | C. Bennett | Medium
BC-003 | PRJ-003 | Approved | 148 | 100 | 0.18 | 11 | PMO | D. Kim | Low
BC-004 | PRJ-004 | Under Review | 162 | 110 | 0.19 | 12 | Business Sponsor | S. Chen | High | 2026-02-02
BC-005 | PRJ-005 | Under Review | 176 | 120 | 0.2 | 13 | SteerCo | M. Lopez | Medium
BC-006 | PRJ-006 | Approved | 190 | 130 | 0.21 | 14 | Finance | R. Torres | Low
BC-007 | PRJ-007 | Pending | 204 | 140 | 0.16 | 15 | PMO | A. Rahman | High | 2026-02-20
BC-008 | PRJ-008 | Approved | 218 | 150 | 0.17 | 16 | Business Sponsor | C. Bennett | Medium
BC-009 | PRJ-009 | Under Review | 232 | 160 | 0.18 | 17 | SteerCo | D. Kim | Low
BC-010 | PRJ-010 | Under Review | 246 | 170 | 0.19 | 9 | Finance | S. Chen | High | 2026-03-10
BC-011 | PRJ-011 | Approved | 260 | 180 | 0.2 | 10 | PMO | M. Lopez | Medium
BC-012 | PRJ-012 | Pending | 274 | 190 | 0.21 | 11 | Business Sponsor | R. Torres | Low
BC-013 | PRJ-013 | Approved | 288 | 200 | 0.16 | 12 | SteerCo | A. Rahman | High | 2026-03-28
BC-014 | PRJ-014 | Under Review | 302 | 210 | 0.17 | 13 | Finance | C. Bennett | Medium
BC-015 | PRJ-015 | Under Review | 316 | 220 | 0.18 | 14 | PMO | D. Kim | Low
BC-016 | PRJ-016 | Approved | 330 | 230 | 0.19 | 15 | Business Sponsor | S. Chen | High | 2026-04-15
BC-017 | PRJ-017 | Pending | 344 | 240 | 0.2 | 16 | SteerCo | M. Lopez | Medium
BC-018 | PRJ-018 | Approved | 358 | 250 | 0.21 | 17 | Finance | R. Torres | Low
BC-019 | PRJ-019 | Under Review | 372 | 260 | 0.16 | 9 | PMO | A. Rahman | High | 2026-05-03
BC-020 | PRJ-020 | Under Review | 386 | 270 | 0.17 | 10 | Business Sponsor | C. Bennett | Medium
BC-021 | PRJ-021 | Approved | 400 | 280 | 0.18 | 11 | SteerCo | D. Kim | Low
BC-022 | PRJ-022 | Pending | 414 | 290 | 0.19 | 12 | Finance | S. Chen | High | 2026-05-21
BC-023 | PRJ-023 | Approved | 428 | 300 | 0.2 | 13 | PMO | M. Lopez | Medium
BC-024 | PRJ-024 | Under Review | 442 | 310 | 0.21 | 14 | Business Sponsor | R. Torres | Low
BC-025 | PRJ-025 | Under Review | 456 | 320 | 0.16 | 15 | SteerCo | A. Rahman | High | 2026-06-08
BC-026 | PRJ-026 | Approved | 470 | 330 | 0.17 | 16 | Finance | C. Bennett | Medium
BC-027 | PRJ-027 | Pending | 484 | 340 | 0.18 | 17 | PMO | D. Kim | Low
BC-028 | PRJ-028 | Approved | 498 | 350 | 0.19 | 9 | Business Sponsor | S. Chen | High | 2026-06-26
BC-029 | PRJ-029 | Under Review | 512 | 360 | 0.2 | 10 | SteerCo | M. Lopez | Medium
BC-030 | PRJ-030 | Under Review | 526 | 370 | 0.21 | 11 | Finance | R. Torres | Low
BC-031 | PRJ-031 | Approved | 540 | 380 | 0.16 | 12 | PMO | A. Rahman | High | 2026-07-14
BC-032 | PRJ-032 | Pending | 554 | 390 | 0.17 | 13 | Business Sponsor | C. Bennett | Medium
BC-033 | PRJ-033 | Approved | 568 | 400 | 0.18 | 14 | SteerCo | D. Kim | Low
BC-034 | PRJ-034 | Under Review | 582 | 410 | 0.19 | 15 | Finance | S. Chen | High | 2026-08-01
BC-035 | PRJ-035 | Under Review | 596 | 420 | 0.2 | 16 | PMO | M. Lopez | Medium
BC-036 | PRJ-036 | Approved | 610 | 430 | 0.21 | 17 | Business Sponsor | R. Torres | Low
BC-037 | PRJ-037 | Pending | 624 | 440 | 0.16 | 9 | SteerCo | A. Rahman | High | 2026-08-19

## 90_Financials (hidden)
FinancialID | ProjectID | Period | Budget | Actual | Committed | Forecast | EAC | Variance | VariancePct | Currency
FN-001-1 | PRJ-001 | 2026-01 | 60 | 50 | 7 | 55 | 58 | -5 | -0.083333 | USD
FN-001-2 | PRJ-001 | 2026-02 | 60 | 53 | 9 | 59 | 58 | -1 | -0.016667 | USD
FN-001-3 | PRJ-001 | 2026-03 | 60 | 56 | 11 | 64 | 58 | 4 | 0.066667 | USD
FN-002-1 | PRJ-002 | 2026-01 | 66 | 56 | 8 | 62 | 65 | -4 | -0.060606 | USD
FN-002-2 | PRJ-002 | 2026-02 | 66 | 59 | 10 | 66 | 65 | 0 | 0 | USD
FN-002-3 | PRJ-002 | 2026-03 | 66 | 63 | 12 | 71 | 65 | 5 | 0.075758 | USD
FN-003-1 | PRJ-003 | 2026-01 | 72 | 62 | 9 | 68 | 73 | -4 | -0.055556 | USD
FN-003-2 | PRJ-003 | 2026-02 | 72 | 66 | 11 | 74 | 73 | 2 | 0.027778 | USD
FN-003-3 | PRJ-003 | 2026-03 | 72 | 69 | 13 | 78 | 73 | 6 | 0.083333 | USD
FN-004-1 | PRJ-004 | 2026-01 | 78 | 68 | 9 | 74 | 82 | -4 | -0.051282 | USD
FN-004-2 | PRJ-004 | 2026-02 | 78 | 72 | 12 | 80 | 82 | 2 | 0.025641 | USD
FN-004-3 | PRJ-004 | 2026-03 | 78 | 76 | 14 | 86 | 82 | 8 | 0.10256 | USD
FN-005-1 | PRJ-005 | 2026-01 | 84 | 71 | 10 | 78 | 91 | -6 | -0.071429 | USD
FN-005-2 | PRJ-005 | 2026-02 | 84 | 75 | 13 | 84 | 91 | 0 | 0 | USD
FN-005-3 | PRJ-005 | 2026-03 | 84 | 79 | 15 | 90 | 91 | 6 | 0.071429 | USD
FN-006-1 | PRJ-006 | 2026-01 | 90 | 77 | 11 | 85 | 86 | -5 | -0.055556 | USD
FN-006-2 | PRJ-006 | 2026-02 | 90 | 81 | 14 | 91 | 86 | 1 | 0.011111 | USD
FN-006-3 | PRJ-006 | 2026-03 | 90 | 86 | 16 | 97 | 86 | 7 | 0.077778 | USD
FN-007-1 | PRJ-007 | 2026-01 | 96 | 83 | 12 | 91 | 95 | -5 | -0.052083 | USD
FN-007-2 | PRJ-007 | 2026-02 | 96 | 87 | 14 | 97 | 95 | 1 | 0.010417 | USD
FN-007-3 | PRJ-007 | 2026-03 | 96 | 92 | 17 | 104 | 95 | 8 | 0.083333 | USD
FN-008-1 | PRJ-008 | 2026-01 | 102 | 89 | 12 | 97 | 104 | -5 | -0.04902 | USD
FN-008-2 | PRJ-008 | 2026-02 | 102 | 94 | 15 | 105 | 104 | 3 | 0.029412 | USD
FN-008-3 | PRJ-008 | 2026-03 | 102 | 99 | 18 | 112 | 104 | 10 | 0.098039 | USD
FN-009-1 | PRJ-009 | 2026-01 | 108 | 91 | 13 | 100 | 113 | -8 | -0.074074 | USD
FN-009-2 | PRJ-009 | 2026-02 | 108 | 96 | 16 | 107 | 113 | -1 | -0.0092593 | USD
FN-009-3 | PRJ-009 | 2026-03 | 108 | 102 | 19 | 115 | 113 | 7 | 0.064815 | USD
FN-010-1 | PRJ-010 | 2026-01 | 114 | 97 | 14 | 107 | 123 | -7 | -0.061404 | USD
FN-010-2 | PRJ-010 | 2026-02 | 114 | 103 | 17 | 115 | 123 | 1 | 0.0087719 | USD
FN-010-3 | PRJ-010 | 2026-03 | 114 | 108 | 21 | 123 | 123 | 9 | 0.078947 | USD
FN-011-1 | PRJ-011 | 2026-01 | 120 | 103 | 14 | 113 | 115 | -7 | -0.058333 | USD
FN-011-2 | PRJ-011 | 2026-02 | 120 | 109 | 18 | 122 | 115 | 2 | 0.016667 | USD
FN-011-3 | PRJ-011 | 2026-03 | 120 | 115 | 22 | 130 | 115 | 10 | 0.083333 | USD
FN-012-1 | PRJ-012 | 2026-01 | 126 | 110 | 15 | 121 | 125 | -5 | -0.039683 | USD
FN-012-2 | PRJ-012 | 2026-02 | 126 | 116 | 19 | 129 | 125 | 3 | 0.02381 | USD
FN-012-3 | PRJ-012 | 2026-03 | 126 | 122 | 23 | 138 | 125 | 12 | 0.095238 | USD
FN-013-1 | PRJ-013 | 2026-01 | 132 | 111 | 16 | 122 | 135 | -10 | -0.075758 | USD
FN-013-2 | PRJ-013 | 2026-02 | 132 | 117 | 20 | 131 | 135 | -1 | -0.0075758 | USD
FN-013-3 | PRJ-013 | 2026-03 | 132 | 124 | 24 | 141 | 135 | 9 | 0.068182 | USD
FN-014-1 | PRJ-014 | 2026-01 | 138 | 117 | 17 | 129 | 145 | -9 | -0.065217 | USD
FN-014-2 | PRJ-014 | 2026-02 | 138 | 124 | 21 | 139 | 145 | 1 | 0.0072464 | USD
FN-014-3 | PRJ-014 | 2026-03 | 138 | 131 | 25 | 149 | 145 | 11 | 0.07971 | USD
FN-015-1 | PRJ-015 | 2026-01 | 144 | 124 | 17 | 136 | 156 | -8 | -0.055556 | USD
FN-015-2 | PRJ-015 | 2026-02 | 144 | 131 | 22 | 146 | 156 | 2 | 0.013889 | USD
FN-015-3 | PRJ-015 | 2026-03 | 144 | 138 | 26 | 156 | 156 | 12 | 0.083333 | USD
FN-016-1 | PRJ-016 | 2026-01 | 150 | 131 | 18 | 144 | 144 | -6 | -0.04 | USD
FN-016-2 | PRJ-016 | 2026-02 | 150 | 138 | 23 | 154 | 144 | 4 | 0.026667 | USD
FN-016-3 | PRJ-016 | 2026-03 | 150 | 146 | 27 | 165 | 144 | 15 | 0.1 | USD
FN-017-1 | PRJ-017 | 2026-01 | 156 | 131 | 19 | 144 | 154 | -12 | -0.076923 | USD
FN-017-2 | PRJ-017 | 2026-02 | 156 | 139 | 23 | 155 | 154 | -1 | -0.0064103 | USD
FN-017-3 | PRJ-017 | 2026-03 | 156 | 147 | 28 | 167 | 154 | 11 | 0.070513 | USD
FN-018-1 | PRJ-018 | 2026-01 | 162 | 138 | 19 | 151 | 165 | -11 | -0.067901 | USD
FN-018-2 | PRJ-018 | 2026-02 | 162 | 146 | 24 | 163 | 165 | 1 | 0.0061728 | USD
FN-018-3 | PRJ-018 | 2026-03 | 162 | 154 | 29 | 174 | 165 | 12 | 0.074074 | USD
FN-019-1 | PRJ-019 | 2026-01 | 168 | 144 | 20 | 158 | 176 | -10 | -0.059524 | USD
FN-019-2 | PRJ-019 | 2026-02 | 168 | 153 | 25 | 171 | 176 | 3 | 0.017857 | USD
FN-019-3 | PRJ-019 | 2026-03 | 168 | 161 | 30 | 182 | 176 | 14 | 0.083333 | USD
FN-020-1 | PRJ-020 | 2026-01 | 174 | 151 | 21 | 166 | 188 | -8 | -0.045977 | USD
FN-020-2 | PRJ-020 | 2026-02 | 174 | 160 | 26 | 178 | 188 | 4 | 0.022989 | USD
FN-020-3 | PRJ-020 | 2026-03 | 174 | 169 | 31 | 191 | 188 | 17 | 0.097701 | USD
FN-021-1 | PRJ-021 | 2026-01 | 180 | 151 | 22 | 166 | 173 | -14 | -0.077778 | USD
FN-021-2 | PRJ-021 | 2026-02 | 180 | 160 | 27 | 179 | 173 | -1 | -0.0055556 | USD
FN-021-3 | PRJ-021 | 2026-03 | 180 | 169 | 32 | 191 | 173 | 11 | 0.061111 | USD
FN-022-1 | PRJ-022 | 2026-01 | 186 | 158 | 22 | 173 | 184 | -13 | -0.069892 | USD
FN-022-2 | PRJ-022 | 2026-02 | 186 | 167 | 28 | 187 | 184 | 1 | 0.0053763 | USD
FN-022-3 | PRJ-022 | 2026-03 | 186 | 177 | 33 | 200 | 184 | 14 | 0.075269 | USD
FN-023-1 | PRJ-023 | 2026-01 | 192 | 165 | 23 | 181 | 196 | -11 | -0.057292 | USD
FN-023-2 | PRJ-023 | 2026-02 | 192 | 175 | 29 | 195 | 196 | 3 | 0.015625 | USD
FN-023-3 | PRJ-023 | 2026-03 | 192 | 184 | 35 | 209 | 196 | 17 | 0.088542 | USD
FN-024-1 | PRJ-024 | 2026-01 | 198 | 172 | 24 | 189 | 208 | -9 | -0.045455 | USD
FN-024-2 | PRJ-024 | 2026-02 | 198 | 182 | 30 | 203 | 208 | 5 | 0.025253 | USD
FN-024-3 | PRJ-024 | 2026-03 | 198 | 192 | 36 | 217 | 208 | 19 | 0.09596 | USD
FN-025-1 | PRJ-025 | 2026-01 | 204 | 171 | 24 | 188 | 220 | -16 | -0.078431 | USD
FN-025-2 | PRJ-025 | 2026-02 | 204 | 182 | 31 | 204 | 220 | 0 | 0 | USD
FN-025-3 | PRJ-025 | 2026-03 | 204 | 192 | 37 | 218 | 220 | 14 | 0.068627 | USD
FN-026-1 | PRJ-026 | 2026-01 | 210 | 179 | 25 | 197 | 202 | -13 | -0.061905 | USD
FN-026-2 | PRJ-026 | 2026-02 | 210 | 189 | 32 | 211 | 202 | 1 | 0.0047619 | USD
FN-026-3 | PRJ-026 | 2026-03 | 210 | 200 | 38 | 227 | 202 | 17 | 0.080952 | USD
FN-027-1 | PRJ-027 | 2026-01 | 216 | 186 | 26 | 204 | 214 | -12 | -0.055556 | USD
FN-027-2 | PRJ-027 | 2026-02 | 216 | 197 | 32 | 219 | 214 | 3 | 0.013889 | USD
FN-027-3 | PRJ-027 | 2026-03 | 216 | 207 | 39 | 234 | 214 | 18 | 0.083333 | USD
FN-028-1 | PRJ-028 | 2026-01 | 222 | 193 | 27 | 212 | 226 | -10 | -0.045045 | USD
FN-028-2 | PRJ-028 | 2026-02 | 222 | 204 | 33 | 227 | 226 | 5 | 0.022523 | USD
FN-028-3 | PRJ-028 | 2026-03 | 222 | 215 | 40 | 243 | 226 | 21 | 0.094595 | USD
FN-029-1 | PRJ-029 | 2026-01 | 228 | 192 | 27 | 211 | 239 | -17 | -0.074561 | USD
FN-029-2 | PRJ-029 | 2026-02 | 228 | 203 | 34 | 227 | 239 | -1 | -0.004386 | USD
FN-029-3 | PRJ-029 | 2026-03 | 228 | 214 | 41 | 243 | 239 | 15 | 0.065789 | USD
FN-030-1 | PRJ-030 | 2026-01 | 234 | 199 | 28 | 219 | 253 | -15 | -0.064103 | USD
FN-030-2 | PRJ-030 | 2026-02 | 234 | 211 | 35 | 236 | 253 | 2 | 0.008547 | USD
FN-030-3 | PRJ-030 | 2026-03 | 234 | 222 | 42 | 251 | 253 | 17 | 0.07265 | USD
FN-031-1 | PRJ-031 | 2026-01 | 240 | 206 | 29 | 226 | 230 | -14 | -0.058333 | USD
FN-031-2 | PRJ-031 | 2026-02 | 240 | 218 | 36 | 243 | 230 | 3 | 0.0125 | USD
FN-031-3 | PRJ-031 | 2026-03 | 240 | 230 | 43 | 260 | 230 | 20 | 0.083333 | USD
FN-032-1 | PRJ-032 | 2026-01 | 246 | 214 | 30 | 235 | 244 | -11 | -0.044715 | USD
FN-032-2 | PRJ-032 | 2026-02 | 246 | 226 | 37 | 252 | 244 | 6 | 0.02439 | USD
FN-032-3 | PRJ-032 | 2026-03 | 246 | 239 | 44 | 270 | 244 | 24 | 0.097561 | USD
FN-033-1 | PRJ-033 | 2026-01 | 252 | 212 | 30 | 233 | 257 | -19 | -0.075397 | USD
FN-033-2 | PRJ-033 | 2026-02 | 252 | 224 | 38 | 251 | 257 | -1 | -0.0039683 | USD
FN-033-3 | PRJ-033 | 2026-03 | 252 | 237 | 45 | 269 | 257 | 17 | 0.06746 | USD
FN-034-1 | PRJ-034 | 2026-01 | 258 | 219 | 31 | 241 | 271 | -17 | -0.065891 | USD
FN-034-2 | PRJ-034 | 2026-02 | 258 | 232 | 39 | 259 | 271 | 1 | 0.003876 | USD
FN-034-3 | PRJ-034 | 2026-03 | 258 | 245 | 46 | 277 | 271 | 19 | 0.073643 | USD
FN-035-1 | PRJ-035 | 2026-01 | 264 | 227 | 32 | 249 | 285 | -15 | -0.056818 | USD
FN-035-2 | PRJ-035 | 2026-02 | 264 | 240 | 40 | 268 | 285 | 4 | 0.015152 | USD
FN-035-3 | PRJ-035 | 2026-03 | 264 | 253 | 48 | 287 | 285 | 23 | 0.087121 | USD
FN-036-1 | PRJ-036 | 2026-01 | 270 | 235 | 32 | 257 | 259 | -13 | -0.048148 | USD
FN-036-2 | PRJ-036 | 2026-02 | 270 | 248 | 41 | 277 | 259 | 7 | 0.025926 | USD
FN-036-3 | PRJ-036 | 2026-03 | 270 | 262 | 49 | 296 | 259 | 26 | 0.096296 | USD
FN-037-1 | PRJ-037 | 2026-01 | 276 | 232 | 33 | 255 | 273 | -21 | -0.076087 | USD
FN-037-2 | PRJ-037 | 2026-02 | 276 | 246 | 41 | 275 | 273 | -1 | -0.0036232 | USD
FN-037-3 | PRJ-037 | 2026-03 | 276 | 259 | 50 | 294 | 273 | 18 | 0.065217 | USD

## 90_Resources (hidden)
ResourceID | ProjectID | PersonID | Role | Department | CapacityHours | AllocatedHours | UtilizationPct | Rate | OverallocatedFlag
RS-001-1 | PRJ-001 | A. Lewis | PM | IT | 80 | 70 | 0.875 | 120 | No
RS-001-2 | PRJ-001 | B. Omar | BA | IT | 80 | 82 | 1.025 | 130 | Yes
RS-002-1 | PRJ-002 | B. Omar | PM | Finance | 80 | 82 | 1.025 | 125 | Yes
RS-002-2 | PRJ-002 | C. Singh | BA | Finance | 80 | 94 | 1.175 | 135 | Yes
RS-002-3 | PRJ-002 | D. Carter | Architect | Finance | 80 | 106 | 1.325 | 145 | Yes
RS-003-1 | PRJ-003 | C. Singh | PM | Marketing | 80 | 94 | 1.175 | 130 | Yes
RS-003-2 | PRJ-003 | D. Carter | BA | Marketing | 80 | 106 | 1.325 | 140 | Yes
RS-004-1 | PRJ-004 | D. Carter | PM | Operations | 80 | 106 | 1.325 | 135 | Yes
RS-004-2 | PRJ-004 | E. Fox | BA | Operations | 80 | 118 | 1.475 | 145 | Yes
RS-004-3 | PRJ-004 | F. Jones | Architect | Operations | 80 | 130 | 1.625 | 155 | Yes
RS-005-1 | PRJ-005 | E. Fox | PM | Legal | 80 | 118 | 1.475 | 140 | Yes
RS-005-2 | PRJ-005 | F. Jones | BA | Legal | 80 | 130 | 1.625 | 150 | Yes
RS-006-1 | PRJ-006 | F. Jones | PM | HR | 80 | 130 | 1.625 | 145 | Yes
RS-006-2 | PRJ-006 | G. Khan | BA | HR | 80 | 70 | 0.875 | 155 | No
RS-006-3 | PRJ-006 | H. Park | Architect | HR | 80 | 82 | 1.025 | 165 | Yes
RS-007-1 | PRJ-007 | G. Khan | PM | IT | 80 | 70 | 0.875 | 150 | No
RS-007-2 | PRJ-007 | H. Park | BA | IT | 80 | 82 | 1.025 | 160 | Yes
RS-008-1 | PRJ-008 | H. Park | PM | Finance | 80 | 82 | 1.025 | 155 | Yes
RS-008-2 | PRJ-008 | A. Lewis | BA | Finance | 80 | 94 | 1.175 | 165 | Yes
RS-008-3 | PRJ-008 | B. Omar | Architect | Finance | 80 | 106 | 1.325 | 175 | Yes
RS-009-1 | PRJ-009 | A. Lewis | PM | Marketing | 80 | 94 | 1.175 | 160 | Yes
RS-009-2 | PRJ-009 | B. Omar | BA | Marketing | 80 | 106 | 1.325 | 170 | Yes
RS-010-1 | PRJ-010 | B. Omar | PM | Operations | 80 | 106 | 1.325 | 165 | Yes
RS-010-2 | PRJ-010 | C. Singh | BA | Operations | 80 | 118 | 1.475 | 175 | Yes
RS-010-3 | PRJ-010 | D. Carter | Architect | Operations | 80 | 130 | 1.625 | 185 | Yes
RS-011-1 | PRJ-011 | C. Singh | PM | Legal | 80 | 118 | 1.475 | 170 | Yes
RS-011-2 | PRJ-011 | D. Carter | BA | Legal | 80 | 130 | 1.625 | 180 | Yes
RS-012-1 | PRJ-012 | D. Carter | PM | HR | 80 | 130 | 1.625 | 175 | Yes
RS-012-2 | PRJ-012 | E. Fox | BA | HR | 80 | 70 | 0.875 | 185 | No
RS-012-3 | PRJ-012 | F. Jones | Architect | HR | 80 | 82 | 1.025 | 195 | Yes
RS-013-1 | PRJ-013 | E. Fox | PM | IT | 80 | 70 | 0.875 | 180 | No
RS-013-2 | PRJ-013 | F. Jones | BA | IT | 80 | 82 | 1.025 | 190 | Yes
RS-014-1 | PRJ-014 | F. Jones | PM | Finance | 80 | 82 | 1.025 | 185 | Yes
RS-014-2 | PRJ-014 | G. Khan | BA | Finance | 80 | 94 | 1.175 | 195 | Yes
RS-014-3 | PRJ-014 | H. Park | Architect | Finance | 80 | 106 | 1.325 | 205 | Yes
RS-015-1 | PRJ-015 | G. Khan | PM | Marketing | 80 | 94 | 1.175 | 190 | Yes
RS-015-2 | PRJ-015 | H. Park | BA | Marketing | 80 | 106 | 1.325 | 200 | Yes
RS-016-1 | PRJ-016 | H. Park | PM | Operations | 80 | 106 | 1.325 | 195 | Yes
RS-016-2 | PRJ-016 | A. Lewis | BA | Operations | 80 | 118 | 1.475 | 205 | Yes
RS-016-3 | PRJ-016 | B. Omar | Architect | Operations | 80 | 130 | 1.625 | 215 | Yes
RS-017-1 | PRJ-017 | A. Lewis | PM | Legal | 80 | 118 | 1.475 | 200 | Yes
RS-017-2 | PRJ-017 | B. Omar | BA | Legal | 80 | 130 | 1.625 | 210 | Yes
RS-018-1 | PRJ-018 | B. Omar | PM | HR | 80 | 130 | 1.625 | 205 | Yes
RS-018-2 | PRJ-018 | C. Singh | BA | HR | 80 | 70 | 0.875 | 215 | No
RS-018-3 | PRJ-018 | D. Carter | Architect | HR | 80 | 82 | 1.025 | 225 | Yes
RS-019-1 | PRJ-019 | C. Singh | PM | IT | 80 | 70 | 0.875 | 210 | No
RS-019-2 | PRJ-019 | D. Carter | BA | IT | 80 | 82 | 1.025 | 220 | Yes
RS-020-1 | PRJ-020 | D. Carter | PM | Finance | 80 | 82 | 1.025 | 215 | Yes
RS-020-2 | PRJ-020 | E. Fox | BA | Finance | 80 | 94 | 1.175 | 225 | Yes
RS-020-3 | PRJ-020 | F. Jones | Architect | Finance | 80 | 106 | 1.325 | 235 | Yes
RS-021-1 | PRJ-021 | E. Fox | PM | Marketing | 80 | 94 | 1.175 | 220 | Yes
RS-021-2 | PRJ-021 | F. Jones | BA | Marketing | 80 | 106 | 1.325 | 230 | Yes
RS-022-1 | PRJ-022 | F. Jones | PM | Operations | 80 | 106 | 1.325 | 225 | Yes
RS-022-2 | PRJ-022 | G. Khan | BA | Operations | 80 | 118 | 1.475 | 235 | Yes
RS-022-3 | PRJ-022 | H. Park | Architect | Operations | 80 | 130 | 1.625 | 245 | Yes
RS-023-1 | PRJ-023 | G. Khan | PM | Legal | 80 | 118 | 1.475 | 230 | Yes
RS-023-2 | PRJ-023 | H. Park | BA | Legal | 80 | 130 | 1.625 | 240 | Yes
RS-024-1 | PRJ-024 | H. Park | PM | HR | 80 | 130 | 1.625 | 235 | Yes
RS-024-2 | PRJ-024 | A. Lewis | BA | HR | 80 | 70 | 0.875 | 245 | No
RS-024-3 | PRJ-024 | B. Omar | Architect | HR | 80 | 82 | 1.025 | 255 | Yes
RS-025-1 | PRJ-025 | A. Lewis | PM | IT | 80 | 70 | 0.875 | 240 | No
RS-025-2 | PRJ-025 | B. Omar | BA | IT | 80 | 82 | 1.025 | 250 | Yes
RS-026-1 | PRJ-026 | B. Omar | PM | Finance | 80 | 82 | 1.025 | 245 | Yes
RS-026-2 | PRJ-026 | C. Singh | BA | Finance | 80 | 94 | 1.175 | 255 | Yes
RS-026-3 | PRJ-026 | D. Carter | Architect | Finance | 80 | 106 | 1.325 | 265 | Yes
RS-027-1 | PRJ-027 | C. Singh | PM | Marketing | 80 | 94 | 1.175 | 250 | Yes
RS-027-2 | PRJ-027 | D. Carter | BA | Marketing | 80 | 106 | 1.325 | 260 | Yes
RS-028-1 | PRJ-028 | D. Carter | PM | Operations | 80 | 106 | 1.325 | 255 | Yes
RS-028-2 | PRJ-028 | E. Fox | BA | Operations | 80 | 118 | 1.475 | 265 | Yes
RS-028-3 | PRJ-028 | F. Jones | Architect | Operations | 80 | 130 | 1.625 | 275 | Yes
RS-029-1 | PRJ-029 | E. Fox | PM | Legal | 80 | 118 | 1.475 | 260 | Yes
RS-029-2 | PRJ-029 | F. Jones | BA | Legal | 80 | 130 | 1.625 | 270 | Yes
RS-030-1 | PRJ-030 | F. Jones | PM | HR | 80 | 130 | 1.625 | 265 | Yes
RS-030-2 | PRJ-030 | G. Khan | BA | HR | 80 | 70 | 0.875 | 275 | No
RS-030-3 | PRJ-030 | H. Park | Architect | HR | 80 | 82 | 1.025 | 285 | Yes
RS-031-1 | PRJ-031 | G. Khan | PM | IT | 80 | 70 | 0.875 | 270 | No
RS-031-2 | PRJ-031 | H. Park | BA | IT | 80 | 82 | 1.025 | 280 | Yes
RS-032-1 | PRJ-032 | H. Park | PM | Finance | 80 | 82 | 1.025 | 275 | Yes
RS-032-2 | PRJ-032 | A. Lewis | BA | Finance | 80 | 94 | 1.175 | 285 | Yes
RS-032-3 | PRJ-032 | B. Omar | Architect | Finance | 80 | 106 | 1.325 | 295 | Yes
RS-033-1 | PRJ-033 | A. Lewis | PM | Marketing | 80 | 94 | 1.175 | 280 | Yes
RS-033-2 | PRJ-033 | B. Omar | BA | Marketing | 80 | 106 | 1.325 | 290 | Yes
RS-034-1 | PRJ-034 | B. Omar | PM | Operations | 80 | 106 | 1.325 | 285 | Yes
RS-034-2 | PRJ-034 | C. Singh | BA | Operations | 80 | 118 | 1.475 | 295 | Yes
RS-034-3 | PRJ-034 | D. Carter | Architect | Operations | 80 | 130 | 1.625 | 305 | Yes
RS-035-1 | PRJ-035 | C. Singh | PM | Legal | 80 | 118 | 1.475 | 290 | Yes
RS-035-2 | PRJ-035 | D. Carter | BA | Legal | 80 | 130 | 1.625 | 300 | Yes
RS-036-1 | PRJ-036 | D. Carter | PM | HR | 80 | 130 | 1.625 | 295 | Yes
RS-036-2 | PRJ-036 | E. Fox | BA | HR | 80 | 70 | 0.875 | 305 | No
RS-036-3 | PRJ-036 | F. Jones | Architect | HR | 80 | 82 | 1.025 | 315 | Yes
RS-037-1 | PRJ-037 | E. Fox | PM | IT | 80 | 70 | 0.875 | 300 | No
RS-037-2 | PRJ-037 | F. Jones | BA | IT | 80 | 82 | 1.025 | 310 | Yes

## 90_StatusUpdates (hidden)
UpdateID | ProjectID | UpdateDate | Reporter | RAG | PercentComplete | Summary | Blockers | NextSteps | DecisionRequired
UP-001 | PRJ-001 | 2026-01-12 | N. Ibrahim | Green | 0.18 | ERP Stabilization remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-002 | PRJ-002 | 2026-01-17 | S. Hall | Green | 0.25 | Client Portal Redesign remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-003 | PRJ-003 | 2026-01-22 | A. Khan | Green | 0.32 | Finance Automation remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-004 | PRJ-004 | 2026-01-27 | M. Singh | Amber | 0.39 | Data Warehouse Refresh remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-005 | PRJ-005 | 2026-02-01 | J. Patel | Amber | 0.46 | Compliance Uplift remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-006 | PRJ-006 | 2026-02-06 | L. Wong | Red | 0.53 | Contact Center Optimization remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-007 | PRJ-007 | 2026-02-11 | N. Ibrahim | Green | 0.6 | ServiceNow Rollout remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-008 | PRJ-008 | 2026-02-16 | S. Hall | Green | 0.67 | Sales Forecast Model remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-009 | PRJ-009 | 2026-02-21 | A. Khan | Green | 0.74 | Procurement Controls remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-010 | PRJ-010 | 2026-02-26 | M. Singh | Amber | 0.81 | HR Self-Service remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-011 | PRJ-011 | 2026-03-03 | J. Patel | Amber | 0.18 | Mobile App Release remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-012 | PRJ-012 | 2026-03-08 | L. Wong | Red | 0.25 | Cloud Cost Optimization remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-013 | PRJ-013 | 2026-03-13 | N. Ibrahim | Green | 0.32 | Portfolio Intake Revamp remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-014 | PRJ-014 | 2026-03-18 | S. Hall | Green | 0.39 | Steering Committee Pack remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-015 | PRJ-015 | 2026-03-23 | A. Khan | Green | 0.46 | Security Hardening remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-016 | PRJ-016 | 2026-03-28 | M. Singh | Amber | 0.53 | CRM Data Quality remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-017 | PRJ-017 | 2026-04-02 | J. Patel | Amber | 0.6 | Resource Planning Model remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-018 | PRJ-018 | 2026-04-07 | L. Wong | Red | 0.67 | Customer Onboarding remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-019 | PRJ-019 | 2026-04-12 | N. Ibrahim | Green | 0.74 | Billing Reconciliation remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-020 | PRJ-020 | 2026-04-17 | S. Hall | Green | 0.81 | Vendor Integration remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-021 | PRJ-021 | 2026-04-22 | A. Khan | Green | 0.18 | Product Discovery remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-022 | PRJ-022 | 2026-04-27 | M. Singh | Amber | 0.25 | Analytics Governance remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-023 | PRJ-023 | 2026-05-02 | J. Patel | Amber | 0.32 | Retention Campaign remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-024 | PRJ-024 | 2026-05-07 | L. Wong | Red | 0.39 | Operational Dashboard remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-025 | PRJ-025 | 2026-05-12 | N. Ibrahim | Green | 0.46 | Policy Refresh remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-026 | PRJ-026 | 2026-05-17 | S. Hall | Green | 0.53 | API Gateway remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-027 | PRJ-027 | 2026-05-22 | A. Khan | Green | 0.6 | Knowledge Base remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-028 | PRJ-028 | 2026-05-27 | M. Singh | Amber | 0.67 | Workflow Simplification remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-029 | PRJ-029 | 2026-06-01 | J. Patel | Amber | 0.74 | Audit Readiness remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-030 | PRJ-030 | 2026-06-06 | L. Wong | Red | 0.81 | Release Train remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-031 | PRJ-031 | 2026-06-11 | N. Ibrahim | Green | 0.18 | Benefits Tracking remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-032 | PRJ-032 | 2026-06-16 | S. Hall | Green | 0.25 | PMO Operating Model remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-033 | PRJ-033 | 2026-06-21 | A. Khan | Green | 0.32 | Capacity Planning remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes
UP-034 | PRJ-034 | 2026-06-26 | M. Singh | Amber | 0.39 | Change Request Hub remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-035 | PRJ-035 | 2026-07-01 | J. Patel | Amber | 0.46 | Milestone Tracker remains amber with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-036 | PRJ-036 | 2026-07-06 | L. Wong | Red | 0.53 | Decision Log remains red with active governance in place. | Vendor dependency, unresolved decisions, and schedule pressure. | Refresh dashboard, confirm owners, and close remaining actions. | No
UP-037 | PRJ-037 | 2026-07-11 | N. Ibrahim | Green | 0.6 | Executive Reporting remains green with active governance in place. | None material. | Refresh dashboard, confirm owners, and close remaining actions. | Yes

## 91_Dimensions (hidden)
Portfolio | IT | Finance | Operations | Marketing | Legal | HR
Department | IT | Finance | Marketing | Operations | Legal | HR
Objective | Operational Efficiency | Revenue Growth | Customer Experience | Risk Reduction | Digital Enablement | Data Modernization
People | A. Rahman | C. Bennett | D. Kim | S. Chen | M. Lopez | R. Torres | J. Patel | L. Wong

## 92_Measures_Config (hidden)
Measure | Intent
Total Active Projects | Count of active project rows
Percent Green | Green projects / active projects
Percent Amber | Amber projects / active projects
Percent Red | Red projects / active projects
Overall Health Score | Average project health score
Budget Variance Percent | (Actual + Committed - Budget) / Budget
Open Critical Risks | Open risks with score >= 15
Overallocated Resources | Resource rows with utilization > 100%

## 93_Refresh_Log (hidden)
Last refresh | 2026-05-10T15:32:00.617Z
Source status | Loaded from modeled workbook generator

## 00_Landing
PX
Dashboard
Executive
Portfolio
Health
RAID
Finance
SteerCo
Capacity

## 01_Executive_Dashboard
Executive Dashboard
Portfolio health, trend direction, and escalation focus
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Health Score |  |  | % Green |  |  | % Amber |  |  | % Red
| 72 |  |  | 51% |  |  | 32% |  |  | 16%
| RAG distribution |  |  | Escalations requiring action |  |  |  | Health trend by month
| Green | 19 |  | ERP Stabilization | N. Ibrahim | Green |  | Jan | 21 | 9 | 6
| Amber | 12 |  | Contact Center Optimization | L. Wong | Red |  | Feb | 22 | 8 | 6
| Red | 6 |  | Cloud Cost Optimization | L. Wong | Red |  | Mar | 22 | 10 | 4
|  |  |  | Customer Onboarding | L. Wong | Red
|  |  |  | Retention Campaign | J. Patel | Amber

## 02_Portfolio_Tracker
Portfolio Tracker
Filterable register with RAG control, milestones, budgets, and owners
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Projects |  |  | At Risk |  |  | Red |  |  | Avg % Complete
| 37 |  |  | 12 |  |  | 6 |  |  | 48%
| Project | PM | Dept | RAG | Budget | Forecast | Status Freshness
| ERP Stabilization | N. Ibrahim | IT | Green | 180 | 134 | 1
| Client Portal Redesign | S. Hall | Finance | Green | 198 | 157 | 2
| Finance Automation | A. Khan | Marketing | Green | 216 | 182 | 3
| Data Warehouse Refresh | M. Singh | Operations | Amber | 234 | 208 | 4
| Compliance Uplift | J. Patel | Legal | Amber | 252 | 216 | 5
| Contact Center Optimization | L. Wong | HR | Red | 270 | 246 | 6
| ServiceNow Rollout | N. Ibrahim | IT | Green | 288 | 276 | 7
| Sales Forecast Model | S. Hall | Finance | Green | 306 | 245 | 8
| Procurement Controls | A. Khan | Marketing | Green | 324 | 250 | 1
| HR Self-Service | M. Singh | Operations | Amber | 342 | 281 | 2
| Mobile App Release | J. Patel | Legal | Amber | 360 | 314 | 3
| Cloud Cost Optimization | L. Wong | HR | Red | 378 | 348 | 4

## 03_Project_Health
Project Health Dashboard
Single-project drill-down for governance reviews
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Selected Project |  |  | Health Score |  |  | % Complete |  |  | Budget Var
| ERP Stabilization |  |  | 86 |  |  | 18% |  |  | -26%
| Milestones |  |  |  | Risks |  |  |  | Issues
| Kickoff | Complete | 2026-01-19 |  | Delivery | Score 6 | Closed |  | Major | In progress | Yes
| Build | On track | 2026-02-06 |  | Commercial | Score 12 | Monitoring
| UAT | At risk | 2026-02-24
| Go-live | Pending | 2026-03-14

## 04_Business_Case_Tracker
Business Case Tracker
Approval funnel, benefits tracking, and payback focus
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Approved |  |  | Under Review |  |  | Benefits at Risk |  |  | Avg Payback
| 15 |  |  | 14 |  |  | 12 |  |  | 13m
| Approval funnel |  |  | Benefits table
| Intake | 18 |  | PRJ-001 | Approved | 120 | 9
| Business review | 12 |  | PRJ-002 | Pending | 134 | 10
| Finance review | 9 |  | PRJ-003 | Approved | 148 | 11
| SteerCo | 7 |  | PRJ-004 | Under Review | 162 | 12
| Approved | 4 |  | PRJ-005 | Under Review | 176 | 13
|  |  |  | PRJ-006 | Approved | 190 | 14
|  |  |  | PRJ-007 | Pending | 204 | 15
|  |  |  | PRJ-008 | Approved | 218 | 16

## 05_RAID_Log_Dashboard
RAID Log Dashboard
Risk, issue, action, and dependency control
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Open Risks |  |  | Open Issues |  |  | Overdue Actions |  |  | Escalated
| 12 |  |  | 0 |  |  | 10 |  |  | 12
| Risk | Project | Score | Status | Owner |  | Issue | Project | Severity | Status | Decision
| Delivery | PRJ-001 | 6 | Closed | A. Rahman |  | IS-001 | PRJ-001 | Major | In progress | Yes
| Commercial | PRJ-001 | 12 | Monitoring | A. Rahman |  | IS-003 | PRJ-003 | Major | In progress | No
| Commercial | PRJ-002 | 12 | Monitoring | C. Bennett |  | IS-005 | PRJ-005 | Major | In progress | Yes
| Technical | PRJ-003 | 20 | Open | D. Kim |  | IS-007 | PRJ-007 | Major | In progress | No
| Resource | PRJ-004 | 10 | Monitoring | S. Chen |  | IS-009 | PRJ-009 | Major | In progress | Yes
| Change | PRJ-004 | 6 | Closed | S. Chen |  | IS-011 | PRJ-011 | Major | In progress | No
| Change | PRJ-005 | 6 | Closed | M. Lopez |  | IS-013 | PRJ-013 | Major | In progress | Yes
| Delivery | PRJ-006 | 12 | Monitoring | R. Torres |  | IS-015 | PRJ-015 | Major | In progress | No

## 06_Financial_Tracking
Financial Tracking
Budget, actual, committed, and forecast control
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Budget |  |  | Actual |  |  | Forecast |  |  | Variance
| $18648 |  |  | $16872 |  |  | $18835 |  |  | $187
| Project | Budget | Actual | Committed | Forecast | Variance
| ERP Stabilization | 180 | 112 | 22 | 134 | -46
| Client Portal Redesign | 198 | 129 | 28 | 157 | -41
| Finance Automation | 216 | 147 | 35 | 182 | -34
| Data Warehouse Refresh | 234 | 166 | 42 | 208 | -26
| Compliance Uplift | 252 | 186 | 30 | 216 | -36
| Contact Center Optimization | 270 | 208 | 38 | 246 | -24
| ServiceNow Rollout | 288 | 230 | 46 | 276 | -12
| Sales Forecast Model | 306 | 190 | 55 | 245 | -61
| Procurement Controls | 324 | 211 | 39 | 250 | -74
| HR Self-Service | 342 | 233 | 48 | 281 | -61

## 07_Resource_Capacity
Resource Capacity Dashboard
Allocation, overload, and role gap control
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Allocated |  |  | Capacity |  |  | Overallocated |  |  | Utilization
| 9260h |  |  | 7360h |  |  | 79 |  |  | 126%
| Project | Role | Dept | Utilization | Overallocated
| PRJ-001 | PM | IT | 88% | No
| PRJ-001 | BA | IT | 102% | Yes
| PRJ-002 | PM | Finance | 102% | Yes
| PRJ-002 | BA | Finance | 118% | Yes
| PRJ-002 | Architect | Finance | 133% | Yes
| PRJ-003 | PM | Marketing | 118% | Yes
| PRJ-003 | BA | Marketing | 133% | Yes
| PRJ-004 | PM | Operations | 133% | Yes
| PRJ-004 | BA | Operations | 148% | Yes
| PRJ-004 | Architect | Operations | 163% | Yes
| PRJ-005 | PM | Legal | 148% | Yes
| PRJ-005 | BA | Legal | 163% | Yes

## 08_Steering_Committee
Steering Committee Reporting
Decision pack, escalations, and actions
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Decisions |  |  | Escalations |  |  | Open Risks |  |  | Aging Items
| 15 |  |  | 9 |  |  | 12 |  |  | 8
| Decision | Owner | Due | Status
| Approve vendor support | Finance | 2026-01-18 | Open
| Confirm scope reduction | PMO | 2026-01-22 | Pending
| Escalate capacity gap | HR | 2026-01-24 | Open
| Close milestone variance | Project Lead | 2026-01-29 | In progress