## RACI Matrix
RACI Matrix
Clarify who is Responsible, Accountable, Consulted, and Informed for each deliverable
Deliverable / Activity | Project Manager | Lead Consultant | Solution Architect | Client Sponsor | Client PO | QA Lead
Project Charter & Kickoff | A | R | C | A | I | I
Requirements Gathering & Analysis | A | R | C | I | R | I
Solution Architecture & Design | I | C | R | I | C | I
Sprint Planning & Backlog Grooming | A | R | C | I | C | I
UI/UX Design & Prototyping | I | A | C | I | R | C
Development & Implementation | I | A | C | I | I | C
Code Review & Quality Gates | I | R | A | I | I | C
Testing & QA Execution | I | C | I | I | C | R
UAT Coordination & Sign-off | A | C | I | I | R | C
Go-Live Decision & Deployment | C | C | C | A | R | C
Post-Launch Support & Hypercare | A | R | C | I | I | R
Retrospective & Lessons Learned | R | R | C | I | C | I
Legend
R | Responsible — Does the work
A | Accountable — Owns the outcome (ONE per row)
C | Consulted — Input sought (two-way)
I | Informed — Kept updated (one-way)

## Instructions
RACI — Rules & Best Practices
Follow these rules to avoid common RACI anti-patterns
| 1 | Every task must have exactly ONE Accountable. More than one means no-one is truly accountable.
| 2 | Responsible can be shared, but keep it minimal. Diffused responsibility slows delivery.
| 3 | Consulted means two-way communication: you must ask before acting, not tell after.
| 4 | Informed is one-way: tell them what happened, do not ask for their approval.
| 5 | Scan each row: if there is no R, the task will not get done.
| 6 | Scan each column: if someone has too many A's, they are a delivery bottleneck.
| 7 | Review the RACI at each project phase gate — roles evolve as context changes.