## 90_Risks (hidden)
RiskID | ProjectID | Category | Likelihood | Impact | Score | Owner | Mitigation | DueDate | Status | AgingDays | EscalatedFlag
RK-001-1 | PRJ-001 | Delivery | 2 | 3 | 6 | A. Rahman | Mitigate erp stabilization risk 1 | 2026-02-04 | Closed | 5 | No
RK-001-2 | PRJ-001 | Commercial | 3 | 4 | 12 | A. Rahman | Mitigate erp stabilization risk 2 | 2026-02-11 | Monitoring | 6 | No
RK-002-1 | PRJ-002 | Commercial | 3 | 4 | 12 | C. Bennett | Mitigate client portal redesign risk 1 | 2026-02-09 | Monitoring | 6 | No
RK-003-1 | PRJ-003 | Technical | 4 | 5 | 20 | D. Kim | Mitigate finance automation risk 1 | 2026-02-14 | Open | 7 | Yes
RK-004-1 | PRJ-004 | Resource | 5 | 2 | 10 | S. Chen | Mitigate data warehouse refresh risk 1 | 2026-02-19 | Monitoring | 8 | No
RK-004-2 | PRJ-004 | Change | 2 | 3 | 6 | S. Chen | Mitigate data warehouse refresh risk 2 | 2026-02-26 | Closed | 9 | No
RK-005-1 | PRJ-005 | Change | 2 | 3 | 6 | M. Lopez | Mitigate compliance uplift risk 1 | 2026-02-24 | Closed | 9 | No
RK-006-1 | PRJ-006 | Delivery | 3 | 4 | 12 | R. Torres | Mitigate contact center optimization risk 1 | 2026-03-01 | Monitoring | 10 | No
RK-007-1 | PRJ-007 | Commercial | 4 | 5 | 20 | A. Rahman | Mitigate servicenow rollout risk 1 | 2026-03-06 | Open | 11 | Yes
RK-007-2 | PRJ-007 | Technical | 5 | 2 | 10 | A. Rahman | Mitigate servicenow rollout risk 2 | 2026-03-13 | Monitoring | 12 | No
RK-008-1 | PRJ-008 | Technical | 5 | 2 | 10 | C. Bennett | Mitigate sales forecast model risk 1 | 2026-03-11 | Monitoring | 12 | No
RK-009-1 | PRJ-009 | Resource | 2 | 3 | 6 | D. Kim | Mitigate procurement controls risk 1 | 2026-03-16 | Closed | 13 | No
RK-010-1 | PRJ-010 | Change | 3 | 4 | 12 | S. Chen | Mitigate hr self-service risk 1 | 2026-03-21 | Monitoring | 14 | No
RK-010-2 | PRJ-010 | Delivery | 4 | 5 | 20 | S. Chen | Mitigate hr self-service risk 2 | 2026-03-28 | Open | 15 | Yes
RK-011-1 | PRJ-011 | Delivery | 4 | 5 | 20 | M. Lopez | Mitigate mobile app release risk 1 | 2026-03-26 | Open | 15 | Yes
RK-012-1 | PRJ-012 | Commercial | 5 | 2 | 10 | R. Torres | Mitigate cloud cost optimization risk 1 | 2026-03-31 | Monitoring | 16 | No
RK-013-1 | PRJ-013 | Technical | 2 | 3 | 6 | A. Rahman | Mitigate portfolio intake revamp risk 1 | 2026-04-05 | Closed | 17 | No
RK-013-2 | PRJ-013 | Resource | 3 | 4 | 12 | A. Rahman | Mitigate portfolio intake revamp risk 2 | 2026-04-12 | Monitoring | 18 | No
RK-014-1 | PRJ-014 | Resource | 3 | 4 | 12 | C. Bennett | Mitigate steering committee pack risk 1 | 2026-04-10 | Monitoring | 18 | No
RK-015-1 | PRJ-015 | Change | 4 | 5 | 20 | D. Kim | Mitigate security hardening risk 1 | 2026-04-15 | Open | 19 | Yes
RK-016-1 | PRJ-016 | Delivery | 5 | 2 | 10 | S. Chen | Mitigate crm data quality risk 1 | 2026-04-20 | Monitoring | 20 | No
RK-016-2 | PRJ-016 | Commercial | 2 | 3 | 6 | S. Chen | Mitigate crm data quality risk 2 | 2026-04-27 | Closed | 21 | No
RK-017-1 | PRJ-017 | Commercial | 2 | 3 | 6 | M. Lopez | Mitigate resource planning model risk 1 | 2026-04-25 | Closed | 21 | No
RK-018-1 | PRJ-018 | Technical | 3 | 4 | 12 | R. Torres | Mitigate customer onboarding risk 1 | 2026-04-30 | Monitoring | 22 | No

## 90_Issues (hidden)
IssueID | ProjectID | Severity | Priority | OpenDate | DueDate | Owner | ResolutionPlan | Status | AgingDays | DecisionRequired
IS-001 | PRJ-001 | Major | High | 2026-01-17 | 2026-01-29 | N. Ibrahim | Resolve erp stabilization blockers through PMO escalation | In progress | 4 | Yes
IS-003 | PRJ-003 | Major | Medium | 2026-01-25 | 2026-02-06 | A. Khan | Resolve finance automation blockers through PMO escalation | In progress | 10 | No
IS-005 | PRJ-005 | Major | Low | 2026-02-02 | 2026-02-14 | J. Patel | Resolve compliance uplift blockers through PMO escalation | In progress | 16 | Yes
IS-007 | PRJ-007 | Major | High | 2026-02-10 | 2026-02-22 | N. Ibrahim | Resolve servicenow rollout blockers through PMO escalation | In progress | 22 | No
IS-009 | PRJ-009 | Major | Medium | 2026-02-18 | 2026-03-02 | A. Khan | Resolve procurement controls blockers through PMO escalation | In progress | 8 | Yes
IS-011 | PRJ-011 | Major | Low | 2026-02-26 | 2026-03-10 | J. Patel | Resolve mobile app release blockers through PMO escalation | In progress | 14 | No
IS-013 | PRJ-013 | Major | High | 2026-03-06 | 2026-03-18 | N. Ibrahim | Resolve portfolio intake revamp blockers through PMO escalation | In progress | 20 | Yes
IS-015 | PRJ-015 | Major | Medium | 2026-03-14 | 2026-03-26 | A. Khan | Resolve security hardening blockers through PMO escalation | In progress | 6 | No
IS-017 | PRJ-017 | Major | Low | 2026-03-22 | 2026-04-03 | J. Patel | Resolve resource planning model blockers through PMO escalation | In progress | 12 | Yes

## 00_Landing
RAID Governance Workbook
Executive RAID command center
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Open Risks |  |  | Open Issues |  |  | Escalated |  |  | Decision Required
| 5 |  |  | 0 |  |  | 5 |  |  | 5
Workbook modules
| RAID Summary | open items and escalation
| Risks | register and mitigation
| Issues | issue log and status
| Actions | ownership and deadlines
| Dependencies | handoffs and blockers

## 01_RAID_Summary
RAID Summary
Open items, aging, and escalation view
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
| Open Risks |  |  | Open Issues |  |  | High Score Risks |  |  | Aging >20
| 5 |  |  | 0 |  |  | 5 |  |  | 3
| Item | Project | Score | Status
| Delivery | PRJ-001 | 6 | Closed
| Commercial | PRJ-001 | 12 | Monitoring
| Commercial | PRJ-002 | 12 | Monitoring
| Technical | PRJ-003 | 20 | Open
| Resource | PRJ-004 | 10 | Monitoring
| Change | PRJ-004 | 6 | Closed
| Change | PRJ-005 | 6 | Closed
| Delivery | PRJ-006 | 12 | Monitoring

## 02_Risks
Risk Register
Probability, impact, score, and mitigation
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
Top risks
| PRJ-001 | Delivery | Score 6 | A. Rahman
| PRJ-001 | Commercial | Score 12 | A. Rahman
| PRJ-002 | Commercial | Score 12 | C. Bennett
| PRJ-003 | Technical | Score 20 | D. Kim
| PRJ-004 | Resource | Score 10 | S. Chen
| PRJ-004 | Change | Score 6 | S. Chen
| PRJ-005 | Change | Score 6 | M. Lopez
| PRJ-006 | Delivery | Score 12 | R. Torres

## 03_Issues
Issue Log
Severity, owner, due date, and status
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
Open issues
| PRJ-001 | Major | In progress | Yes
| PRJ-003 | Major | In progress | No
| PRJ-005 | Major | In progress | Yes
| PRJ-007 | Major | In progress | No
| PRJ-009 | Major | In progress | Yes
| PRJ-011 | Major | In progress | No
| PRJ-013 | Major | In progress | Yes
| PRJ-015 | Major | In progress | No

## 04_Actions
Action Log
Overdue actions and commitments
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
Action log
| Approve mitigation plan | PMO | 2026-01-18
| Confirm vendor escalation | Commercial | 2026-01-22
| Close blocked dependency | Delivery | 2026-01-27
| Review aging issues | SteerCo | 2026-01-29

## 05_Dependencies
Dependency Tracker
Cross-workstream handoffs and blockers
| Home | Executive | Portfolio | Project | Business | RAID | Finance | Capacity | SteerCo
Dependency map
| Payments | Core banking API | Due week 12
| Compliance | Transaction logging | Due week 16
| Data | Source system access | Due week 10
| Change | SteerCo approval | Due next meeting