## Dashboard
Stakeholder Dashboard
Power-Interest Grid · Live counts from your register
| TOTAL STAKEHOLDERS | MANAGE CLOSELY | CHAMPIONS
📊 Power-Interest Grid
▲ HIGH INFLUENCE
MANAGE CLOSELY High Interest · High Influence Proactive, collaborative engagement
KEEP INFORMED High Interest · Low Influence Regular comms, feedback channels
| ◄ LOW INTEREST | HIGH INTEREST ►

## Register
Stakeholder Register
Map all stakeholders · Quadrant auto-assigns based on Interest + Influence
Name | Role / Title | Organisation | Interest | Influence | Quadrant | Comm. Channel | Frequency | Key Concerns | Engagement Strategy | Sentiment | Relationship Owner
Rachel Torres | CEO / Executive Sponsor | Meridian Corp (Client) | H | H | Manage Closely | Executive Briefing | Bi-weekly | ROI, timeline adherence, board reporting | Proactive updates; own the escalation path; no surprises | Champion | Maria Lopez
Tom Nguyen | Product Owner | Meridian Corp (Client) | H | H | Manage Closely | Slack + Weekly Sync | Weekly | Feature completeness, user adoption metrics | Collaborative backlog sessions; co-own priorities | Champion | James Park
Lisa Patel | Head of IT | Meridian Corp (Client) | H | M | Keep Informed | Email + Monthly Review | Monthly | Security posture, integration stability, maintenance | Technical deep-dives; architecture walkthroughs | Neutral | David Kim
Mark Johnson | CFO | Meridian Corp (Client) | L | H | Keep Satisfied | Executive Summary | Monthly | Budget adherence, cost-benefit realisation | Concise financial reporting only; no detail noise | Neutral | Maria Lopez
Sarah Chen | Project Manager | Praxiox (Delivery) | H | M | Keep Informed | Daily Standup | Daily | Delivery risk, team capacity, scope control | Full transparency; early warning system | Supportive | Maria Lopez
Dev Team (6) | Engineering Squad | Praxiox (Delivery) | M | L | Monitor | Sprint Ceremonies | Per Sprint | Clear requirements, stable scope, no context switching | Shield from external noise; clear prioritisation | Neutral | Sarah Chen
End Users (50+) | Operations Staff | Meridian Corp (Client) | H | L | Keep Informed | Newsletter + Training | Bi-weekly | Ease of use, training quality, workflow disruption | Early demos, feedback loops, champions programme | Anxious | Tom Nguyen
Compliance Team | Regulatory & Legal | Meridian Corp (Client) | M | M | Keep Informed | Review Sessions | As Needed | Data privacy, audit trail, GDPR compliance | Involve in design reviews for regulated features | Cautious | David Kim